## ppr
ID. | Category | Load Description | Priority | Truck Type | Rig Down Dependencies | Rig Up Dependencies | Avg Rig Down Time (± Margin) | Avg Rig Up Time (± Margin) | Critical Operation | Floor Men | Roustabouts | Electrician | Mechanics | Welder/Safety
1 | Camp Site | J CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
2 | Camp Site | K CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
3 | Camp Site | DRY STORE / COLD STORE | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 0 | 0 | 0
4 | Camp Site | SENIOR RECREATION | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
5 | Camp Site | JUNIOR RECREATION | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
6 | Camp Site | SENIOR KITCHEN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
7 | Camp Site | SENIOR MESS | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
8 | Camp Site | JUNIOR KITCHEN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
9 | Camp Site | JUNIOR MESS | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
10 | Camp Site | L CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
11 | Camp Site | M CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
12 | Camp Site | N CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
13 | Camp Site | O CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
14 | Camp Site | P CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
15 | Camp Site | Q CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
16 | Camp Site | R CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
17 | Camp Site | S CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
18 | Camp Site | JUNIOR BATH | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
19 | Camp Site | VIP CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
20 | Camp Site | H CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
21 | Camp Site | I CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
22 | Camp Site | C CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
23 | Camp Site | B CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
24 | Camp Site | A CARAVAN | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
25 | Camp Site | LAUNDRY | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 0 | 0 | 0
26 | Camp Site | JUNIOR BATH | Priority 1 | FLAT BED | 32 | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
27 | Camp Site | CAMP GENERATOR | Priority 1 | LOW BED | None | None | 1 Hr ± 0.5 Hrs | 1.5 Hrs ± 0.5 Hrs | Yes | 1 | 4 | 2 | 0 | 0
28 | Camp Site | FUEL TANK | Priority 1 | LOW BED | None | None | 1 Hr ± 0.5 Hrs | 1.5 Hrs ± 0.5 Hrs | Yes | 2 | 4 | 0 | 0 | 0
29 | Camp Site | WATER TANK-1 | Priority 1 | FLAT BED | None | None | 1 Hr ± 0.5 Hrs | 1.5 Hrs ± 0.5 Hrs | Yes | 2 | 4 | 0 | 0 | 0
30 | Camp Site | WATER TANK-2 | Priority 1 | FLAT BED | None | None | 1 Hr ± 0.5 Hrs | 1.5 Hrs ± 0.5 Hrs | No | 2 | 4 | 0 | 0 | 0
31 | Camp Site | MOSQUE | Priority 1 | FLAT BED | None | None | 4 Hrs ± 1 Hr (Total Camp) | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 0 | 0 | 0
32 | Camp Site | SEWERAGE LINES | Priority 1 | FLAT BED | None | 46048 | 2 Hrs ± 0.5 Hrs | 3 Hrs ± 1 Hr | Yes | 1 | 4 | 0 | 0 | 0
33 | Rig Site | Mast Section 1(A) | Priority 2 | FLAT BED | 69 | 38 | 8 Hrs ± 1 Hr (System Total) | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
34 | Rig Site | Mast Section 2 | Priority 2 | FLAT BED | 69 | 38 | 8 Hrs ± 1 Hr (System Total) | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
35 | Rig Site | 2 pieces Mast Section 2 | Priority 2 | FLAT BED | 69 | 38 | 8 Hrs ± 1 Hr (System Total) | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
36 | Rig Site | 2 pieces Mast Section 3 | Priority 2 | FLAT BED | 69 | 38 | 8 Hrs ± 1 Hr (System Total) | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
37 | Rig Site | Mast A-Frame | Priority 2 | FLAT BED | 69 | 38 | 8 Hrs ± 1 Hr (System Total) | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
38 | Rig Site | Sub-base & Gin Pole 1 | Priority 2 | HH (48 ft) | 33 | None | 8 Hrs ± 1 Hr (System Total) | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
39 | Rig Site | Sub-base & Gin Pole 2 | Priority 2 | HH (48 ft) | 33 | None | 8 Hrs ± 1 Hr (System Total) | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
40 | Rig Site | Monkey board & Rig Floor | Priority 2 | FLAT BED | None | 62 | 8 Hrs ± 1 Hr (System Total) | Not Specified | Yes | 1 | 2 | 0 | 0 | 0
41 | Rig Site | Drawworks set back | Priority 2 | FLAT BED | None | 62 | 8 Hrs ± 1 Hr (System Total) | Not Specified | Yes | 4 | 2 | 0 | 1 | 0
42 | Rig Site | MAST SUPPORTS | Priority 2 | FLAT BED | 69 | 38 | 8 Hrs ± 1 Hr (System Total) | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
43 | Rig Site | Crown Block (Mast B) | Priority 2 | LOW BED | 69 | 38 | 8 Hrs ± 1 Hr (System Total) | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
44 | Rig Site | ACTIVE MUD TANK-1 | Priority 2 | LOW BED | None | 49 | 12 Hrs ± 1 Hr (System Total) | 20 Hrs ± 2 Hrs (System Total) | Yes | 2 | 4 | 1 | 1 | 0
45 | Rig Site | ACTIVE MUD TANK-2 | Priority 2 | LOW BED | None | 49 | 12 Hrs ± 1 Hr (System Total) | 20 Hrs ± 2 Hrs (System Total) | Yes | 2 | 4 | 1 | 1 | 0
46 | Rig Site | RESERVE MUD TANK-1 | Priority 2 | LOW BED | None | 49 | 12 Hrs ± 1 Hr (System Total) | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 1 | 1 | 0
47 | Rig Site | RESERVE MUD TANK-2 | Priority 2 | LOW BED | None | 49 | 12 Hrs ± 1 Hr (System Total) | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 1 | 1 | 0
48 | Rig Site | TREATMENT TANK/DEGASSER TANK | Priority 2 | LOW BED | None | 49 | 12 Hrs ± 1 Hr (System Total) | 20 Hrs ± 2 Hrs (System Total) | Yes | 1 | 2 | 0 | 0 | 0
49 | Rig Site | RIG WATER TANK + HOPPERS | Priority 2 | LOW BED | None | None | 2 Hrs ± 0.5 Hrs (System Total) | 20 Hrs ± 2 Hrs (System Total) | Yes | 2 | 4 | 0 | 0 | 0
50 | Rig Site | SPARE MUD TANK (BLUE) | Priority 2 | LOW BED | None | 49 | 12 Hrs ± 1 Hr (System Total) | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 1 | 1 | 0
51 | Rig Site | PCR (Power Control Room) | Priority 2 | LOW BED | None | None | Not Specified | Not Specified | Yes | 1 | 2 | 2 | 0 | 0
52 | Rig Site | MUD PUMP-1 | Priority 2 | LOW BED | 44 | 44 | 2 Hrs ± 0.5 Hrs | 3 Hrs ± 0.5 Hrs | Yes | 3 | 2 | 0 | 2 | 0
53 | Rig Site | MUD PUM-2 | Priority 2 | LOW BED | 44 | 44 | 2 Hrs ± 0.5 Hrs | 3 Hrs ± 0.5 Hrs | Yes | 1 | 2 | 0 | 0 | 0
54 | Rig Site | TRIP TANK SKID | Priority 2 | LOW BED | None | 49 | 12 Hrs ± 1 Hr (System Total) | 20 Hrs ± 2 Hrs (System Total) | Yes | 1 | 2 | 0 | 0 | 0
55 | Rig Site | SHAKER SKID | Priority 2 | LOW BED | None | 49 | 12 Hrs ± 1 Hr (System Total) | 20 Hrs ± 2 Hrs (System Total) | Yes | 2 | 4 | 0 | 0 | 0
56 | Rig Site | SHAKER SKID WALK WAY-RIGHT | Priority 2 | LOW BED | None | 49 | 12 Hrs ± 1 Hr (System Total) | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 0 | 0 | 0
57 | Rig Site | SHAKER SKID WALKWAY - LEFT | Priority 2 | LOW BED | None | 49 | 12 Hrs ± 1 Hr (System Total) | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 0 | 0 | 0
58 | Rig Site | RIG ENGINE # 1 | Priority 2 | LOW BED | None | 51 | 10 Hrs ± 1 Hr (System Total) | 5 Hrs ± 1 Hr (System Total) | Yes | 3 | 2 | 0 | 2 | 0
59 | Rig Site | RIG ENGINE # 2 | Priority 2 | LOW BED | None | 51 | 10 Hrs ± 1 Hr (System Total) | 5 Hrs ± 1 Hr (System Total) | Yes | 3 | 2 | 0 | 2 | 0
60 | Rig Site | RIG ENGINE # 3 | Priority 2 | LOW BED | None | 51 | 10 Hrs ± 1 Hr (System Total) | 5 Hrs ± 1 Hr (System Total) | Yes | 3 | 2 | 0 | 2 | 0
61 | Rig Site | KOOMY SKID (Accumulator) | Priority 2 | LOW BED | None | None | 4 Hrs ± 0.5 Hrs | 5 Hrs ± 0.5 Hrs | Yes | 1 | 2 | 0 | 1 | 0
62 | Rig Site | DRAWORKS | Priority 2 | LOW BED | 33 | 38 | 1 Hr ± 0.25 Hrs | 2.5 Hrs ± 0.5 Hrs | Yes | 1 | 2 | 0 | 0 | 0
63 | Rig Site | WHITE WATER TANK + GROUND HOPPER | Priority 2 | FLAT BED | None | None | 2 Hrs ± 0.5 Hrs (System Total) | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 0 | 0 | 0
64 | Rig Site | GROSS HOPPER | Priority 2 | FLAT BED | None | 62 | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 0
65 | Rig Site | COOLING SKID | Priority 2 | FLAT BED | None | 49 | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 0
66 | Rig Site | FLARE LINES / RACKS | Priority 2 | FLAT BED | None | 62 | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 1
67 | Rig Site | Drill Pipe set back & Rotary table beams | Priority 2 | FLAT BED | None | 62 | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
68 | Rig Site | X-OVER BASKET | Priority 2 | FLAT BED | None | 62 | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
69 | Rig Site | CATWALK / MOUSE HOLE | Priority 2 | FLAT BED | None | 62 | Not Specified | Not Specified | Yes | 2 | 4 | 0 | 0 | 0
70 | Rig Site | RIG TOILET + SULAIR COMPRESSOR | Priority 2 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 0 | 1 | 0
71 | Rig Site | OIL BASKET | Priority 2 | FLAT BED | None | None | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
72 | Rig Site | MECHANICAL BASKET | Priority 2 | FLAT BED | None | None | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
73 | Rig Site | ELECTRIC BASKET | Priority 2 | FLAT BED | None | None | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
74 | Rig Site | TRAINING ROOM | Priority 2 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 1 | 0 | 0
75 | Rig Site | DIESEL TANK -1 | Priority 2 | LOW BED | None | None | 5 Hrs ± 1 Hr (System Total) | 5 Hrs ± 1 Hr (System Total) | Yes | 1 | 2 | 0 | 0 | 0
76 | Rig Site | DIESEL TANK-2 | Priority 2 | LOW BED | None | None | 5 Hrs ± 1 Hr (System Total) | 5 Hrs ± 1 Hr (System Total) | No | 1 | 2 | 0 | 0 | 0
77 | Rig Site | CSG HANDLING DSA BASKET | Priority 2 | LOW BED | None | None | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
78 | Rig Site | BOP SKID STUMP 13 5/8" | Priority 2 | LOW BED | None | 62 | Not Specified | Not Specified | Yes | 3 | 2 | 0 | 0 | 0
79 | Rig Site | SUPER CHARGER SKID | Priority 2 | LOW BED | None | 44 | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 0
80 | Rig Site | DRILLER SHELTER/HYD UNIT | Priority 2 | LOW BED | None | 62 | Not Specified | Not Specified | Yes | 1 | 2 | 0 | 0 | 0
81 | Rig Site | POOR BOY DEGASSER/CHOKEMANIFOLD | Priority 2 | LOW BED | None | 44 | 2 Hrs ± 0.5 Hrs | Not Specified | Yes | 3 | 2 | 0 | 0 | 0
82 | Rig Site | DRILL COLLAR BASKET 4 3/4" | Priority 2 | HEAVY HAULER | None | 62 | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
83 | Rig Site | 3 1/2" DRILL PIPE BASKET #1(G-11) | Priority 2 | HEAVY HAULER | None | 62 | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
84 | Rig Site | 3 1/2" DRILL PIPE BASKET #2 (G-11) | Priority 2 | HEAVY HAULER | None | 62 | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
85 | Rig Site | 3 1/2" DRILL PIPE BASKET #3(G-11) | Priority 2 | HEAVY HAULER | None | 62 | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
86 | Rig Site | 3 1/2" DRILL PIPE BASKET #4 (G-111) | Priority 2 | HEAVY HAULER | None | 62 | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
87 | Rig Site | 3 1/2" DRILL PIPE BASEKT #5 (S-135) | Priority 2 | HEAVY HAULER | None | 62 | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
88 | Rig Site | NO CHARGE STORE | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 0
89 | Rig Site | RUBBER STORE | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 0
90 | Rig Site | FISHING STORE | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 0
91 | Rig Site | DRILLING STORE | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 0
92 | Rig Site | ELECTRIC STORE | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 0
93 | Rig Site | MECHANICAL STORE | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 0
94 | Rig Site | WELDING SHOP | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 1
95 | Rig Site | PAINT STORE / BOP STORE | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 3 | 2 | 0 | 0 | 0
96 | Rig Site | MECHANICAL/ELECTRIC WORKSHOP | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 0
97 | Rig Site | PMS OFFICE | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 4 | 1 | 0 | 0
98 | Rig Site | TOOL PUSHER OFFICE | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 4 | 1 | 0 | 0
99 | Rig Site | COMPANY MAN OFFICE | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 4 | 1 | 0 | 0
100 | Rig Site | CLINIC | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | Yes | 1 | 2 | 1 | 0 | 1
101 | Rig Site | MIC LIVING / RIG MANAGER CARAVAN | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 4 | 1 | 0 | 0
102 | Rig Site | GEOLOGIST ROOM/RADIO ROOM | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 1 | 0 | 0
103 | Rig Site | WATER TANKS RIG CAMP | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
104 | Rig Site | KOOMY LINES / LADERS | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | Yes | 1 | 2 | 0 | 1 | 0
105 | Rig Site | WELDERS BASKET | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 2 | 4 | 0 | 0 | 0
106 | Rig Site | SAFETY CONTAINER | Priority 3 | FLAT BED | None | None | Not Specified | Not Specified | No | 1 | 2 | 0 | 0 | 1

## S1
ID | Phase | Category | Load Description | Priority | Truck Type | Dependency ID | Avg Time (± Margin) | Critical Operation | Floor Men | Roustabouts | Electrician | Mechanics | Welder/Safety
1 | Rig Down | Camp Site | J CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
2 | Rig Up | Camp Site | J CARAVAN | Priority 1 | FLAT BED | 1 | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
3 | Rig Down | Camp Site | K CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
4 | Rig Up | Camp Site | K CARAVAN | Priority 1 | FLAT BED | 3 | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
5 | Rig Down | Camp Site | DRY STORE / COLD STORE | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 0 | 0 | 0
6 | Rig Up | Camp Site | DRY STORE / COLD STORE | Priority 1 | FLAT BED | 5 | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 0 | 0 | 0
7 | Rig Down | Camp Site | SENIOR RECREATION | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
8 | Rig Up | Camp Site | SENIOR RECREATION | Priority 1 | FLAT BED | 7 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
9 | Rig Down | Camp Site | JUNIOR RECREATION | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
10 | Rig Up | Camp Site | JUNIOR RECREATION | Priority 1 | FLAT BED | 9 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
11 | Rig Down | Camp Site | SENIOR KITCHEN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
12 | Rig Up | Camp Site | SENIOR KITCHEN | Priority 1 | FLAT BED | 11 | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
13 | Rig Down | Camp Site | SENIOR MESS | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
14 | Rig Up | Camp Site | SENIOR MESS | Priority 1 | FLAT BED | 13 | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
15 | Rig Down | Camp Site | JUNIOR KITCHEN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
16 | Rig Up | Camp Site | JUNIOR KITCHEN | Priority 1 | FLAT BED | 15 | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
17 | Rig Down | Camp Site | JUNIOR MESS | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
18 | Rig Up | Camp Site | JUNIOR MESS | Priority 1 | FLAT BED | 17 | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
19 | Rig Down | Camp Site | L CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
20 | Rig Up | Camp Site | L CARAVAN | Priority 1 | FLAT BED | 19 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
21 | Rig Down | Camp Site | M CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
22 | Rig Up | Camp Site | M CARAVAN | Priority 1 | FLAT BED | 21 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
23 | Rig Down | Camp Site | N CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
24 | Rig Up | Camp Site | N CARAVAN | Priority 1 | FLAT BED | 23 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
25 | Rig Down | Camp Site | O CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
26 | Rig Up | Camp Site | O CARAVAN | Priority 1 | FLAT BED | 25 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
27 | Rig Down | Camp Site | P CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
28 | Rig Up | Camp Site | P CARAVAN | Priority 1 | FLAT BED | 27 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
29 | Rig Down | Camp Site | Q CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
30 | Rig Up | Camp Site | Q CARAVAN | Priority 1 | FLAT BED | 29 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
31 | Rig Down | Camp Site | R CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
32 | Rig Up | Camp Site | R CARAVAN | Priority 1 | FLAT BED | 31 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
33 | Rig Down | Camp Site | S CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
34 | Rig Up | Camp Site | S CARAVAN | Priority 1 | FLAT BED | 33 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
35 | Rig Down | Camp Site | JUNIOR BATH | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
36 | Rig Up | Camp Site | JUNIOR BATH | Priority 1 | FLAT BED | 35 | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
37 | Rig Down | Camp Site | VIP CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
38 | Rig Up | Camp Site | VIP CARAVAN | Priority 1 | FLAT BED | 37 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
39 | Rig Down | Camp Site | H CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
40 | Rig Up | Camp Site | H CARAVAN | Priority 1 | FLAT BED | 39 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
41 | Rig Down | Camp Site | I CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
42 | Rig Up | Camp Site | I CARAVAN | Priority 1 | FLAT BED | 41 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
43 | Rig Down | Camp Site | C CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
44 | Rig Up | Camp Site | C CARAVAN | Priority 1 | FLAT BED | 43 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
45 | Rig Down | Camp Site | B CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
46 | Rig Up | Camp Site | B CARAVAN | Priority 1 | FLAT BED | 45 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
47 | Rig Down | Camp Site | A CARAVAN | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
48 | Rig Up | Camp Site | A CARAVAN | Priority 1 | FLAT BED | 47 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 1 | 0 | 0
49 | Rig Down | Camp Site | LAUNDRY | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 0 | 0 | 0
50 | Rig Up | Camp Site | LAUNDRY | Priority 1 | FLAT BED | 49 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 0 | 0 | 0
51 | Rig Down | Camp Site | JUNIOR BATH | Priority 1 | FLAT BED | 63 | 4 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
52 | Rig Up | Camp Site | JUNIOR BATH | Priority 1 | FLAT BED | 51 | 5 Hrs ± 1 Hr (Total Camp) | Yes | 1 | 4 | 1 | 0 | 0
53 | Rig Down | Camp Site | CAMP GENERATOR | Priority 1 | LOW BED | None | 1 Hr ± 0.5 Hrs | Yes | 1 | 4 | 2 | 0 | 0
54 | Rig Up | Camp Site | CAMP GENERATOR | Priority 1 | LOW BED | 53 | 1.5 Hrs ± 0.5 Hrs | Yes | 1 | 4 | 2 | 0 | 0
55 | Rig Down | Camp Site | FUEL TANK | Priority 1 | LOW BED | None | 1 Hr ± 0.5 Hrs | Yes | 2 | 4 | 0 | 0 | 0
56 | Rig Up | Camp Site | FUEL TANK | Priority 1 | LOW BED | 55 | 1.5 Hrs ± 0.5 Hrs | Yes | 2 | 4 | 0 | 0 | 0
57 | Rig Down | Camp Site | WATER TANK-1 | Priority 1 | FLAT BED | None | 1 Hr ± 0.5 Hrs | Yes | 2 | 4 | 0 | 0 | 0
58 | Rig Up | Camp Site | WATER TANK-1 | Priority 1 | FLAT BED | 57 | 1.5 Hrs ± 0.5 Hrs | Yes | 2 | 4 | 0 | 0 | 0
59 | Rig Down | Camp Site | WATER TANK-2 | Priority 1 | FLAT BED | None | 1 Hr ± 0.5 Hrs | No | 2 | 4 | 0 | 0 | 0
60 | Rig Up | Camp Site | WATER TANK-2 | Priority 1 | FLAT BED | 59 | 1.5 Hrs ± 0.5 Hrs | No | 2 | 4 | 0 | 0 | 0
61 | Rig Down | Camp Site | MOSQUE | Priority 1 | FLAT BED | None | 4 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 0 | 0 | 0
62 | Rig Up | Camp Site | MOSQUE | Priority 1 | FLAT BED | 61 | 5 Hrs ± 1 Hr (Total Camp) | No | 1 | 4 | 0 | 0 | 0
63 | Rig Down | Camp Site | SEWERAGE LINES | Priority 1 | FLAT BED | None | 2 Hrs ± 0.5 Hrs | Yes | 1 | 4 | 0 | 0 | 0
64 | Rig Up | Camp Site | SEWERAGE LINES | Priority 1 | FLAT BED | 63 | 3 Hrs ± 1 Hr | Yes | 1 | 4 | 0 | 0 | 0
65 | Rig Down | Rig Site | Mast Section 1(A) | Priority 2 | FLAT BED | 137 | 8 Hrs ± 1 Hr (System Total) | Yes | 4 | 2 | 0 | 0 | 0
66 | Rig Up | Rig Site | Mast Section 1(A) | Priority 2 | FLAT BED | 76 ¦ 65 | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
67 | Rig Down | Rig Site | Mast Section 2 | Priority 2 | FLAT BED | 137 | 8 Hrs ± 1 Hr (System Total) | Yes | 4 | 2 | 0 | 0 | 0
68 | Rig Up | Rig Site | Mast Section 2 | Priority 2 | FLAT BED | 76 ¦ 67 | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
69 | Rig Down | Rig Site | 2 pieces Mast Section 2 | Priority 2 | FLAT BED | 137 | 8 Hrs ± 1 Hr (System Total) | Yes | 4 | 2 | 0 | 0 | 0
70 | Rig Up | Rig Site | 2 pieces Mast Section 2 | Priority 2 | FLAT BED | 76 ¦ 69 | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
71 | Rig Down | Rig Site | 2 pieces Mast Section 3 | Priority 2 | FLAT BED | 137 | 8 Hrs ± 1 Hr (System Total) | Yes | 4 | 2 | 0 | 0 | 0
72 | Rig Up | Rig Site | 2 pieces Mast Section 3 | Priority 2 | FLAT BED | 76 ¦ 71 | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
73 | Rig Down | Rig Site | Mast A-Frame | Priority 2 | FLAT BED | 137 | 8 Hrs ± 1 Hr (System Total) | Yes | 4 | 2 | 0 | 0 | 0
74 | Rig Up | Rig Site | Mast A-Frame | Priority 2 | FLAT BED | 76 ¦ 73 | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
75 | Rig Down | Rig Site | Sub-base & Gin Pole 1 | Priority 2 | HH (48 ft) | 65 | 8 Hrs ± 1 Hr (System Total) | Yes | 4 | 2 | 0 | 0 | 0
76 | Rig Up | Rig Site | Sub-base & Gin Pole 1 | Priority 2 | HH (48 ft) | 75 | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
77 | Rig Down | Rig Site | Sub-base & Gin Pole 2 | Priority 2 | HH (48 ft) | 65 | 8 Hrs ± 1 Hr (System Total) | Yes | 4 | 2 | 0 | 0 | 0
78 | Rig Up | Rig Site | Sub-base & Gin Pole 2 | Priority 2 | HH (48 ft) | 77 | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
79 | Rig Down | Rig Site | Monkey board & Rig Floor | Priority 2 | FLAT BED | None | 8 Hrs ± 1 Hr (System Total) | Yes | 1 | 2 | 0 | 0 | 0
80 | Rig Up | Rig Site | Monkey board & Rig Floor | Priority 2 | FLAT BED | 124 ¦ 79 | Not Specified | Yes | 1 | 2 | 0 | 0 | 0
81 | Rig Down | Rig Site | Drawworks set back | Priority 2 | FLAT BED | None | 8 Hrs ± 1 Hr (System Total) | Yes | 4 | 2 | 0 | 1 | 0
82 | Rig Up | Rig Site | Drawworks set back | Priority 2 | FLAT BED | 124 ¦ 81 | Not Specified | Yes | 4 | 2 | 0 | 1 | 0
83 | Rig Down | Rig Site | MAST SUPPORTS | Priority 2 | FLAT BED | 137 | 8 Hrs ± 1 Hr (System Total) | Yes | 4 | 2 | 0 | 0 | 0
84 | Rig Up | Rig Site | MAST SUPPORTS | Priority 2 | FLAT BED | 76 ¦ 83 | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
85 | Rig Down | Rig Site | Crown Block (Mast B) | Priority 2 | LOW BED | 137 | 8 Hrs ± 1 Hr (System Total) | Yes | 4 | 2 | 0 | 0 | 0
86 | Rig Up | Rig Site | Crown Block (Mast B) | Priority 2 | LOW BED | 76 ¦ 85 | Not Specified | Yes | 4 | 2 | 0 | 0 | 0
87 | Rig Down | Rig Site | ACTIVE MUD TANK-1 | Priority 2 | LOW BED | None | 12 Hrs ± 1 Hr (System Total) | Yes | 2 | 4 | 1 | 1 | 0
88 | Rig Up | Rig Site | ACTIVE MUD TANK-1 | Priority 2 | LOW BED | 98 ¦ 87 | 20 Hrs ± 2 Hrs (System Total) | Yes | 2 | 4 | 1 | 1 | 0
89 | Rig Down | Rig Site | ACTIVE MUD TANK-2 | Priority 2 | LOW BED | None | 12 Hrs ± 1 Hr (System Total) | Yes | 2 | 4 | 1 | 1 | 0
90 | Rig Up | Rig Site | ACTIVE MUD TANK-2 | Priority 2 | LOW BED | 98 ¦ 89 | 20 Hrs ± 2 Hrs (System Total) | Yes | 2 | 4 | 1 | 1 | 0
91 | Rig Down | Rig Site | RESERVE MUD TANK-1 | Priority 2 | LOW BED | None | 12 Hrs ± 1 Hr (System Total) | No | 2 | 4 | 1 | 1 | 0
92 | Rig Up | Rig Site | RESERVE MUD TANK-1 | Priority 2 | LOW BED | 98 ¦ 91 | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 1 | 1 | 0
93 | Rig Down | Rig Site | RESERVE MUD TANK-2 | Priority 2 | LOW BED | None | 12 Hrs ± 1 Hr (System Total) | No | 2 | 4 | 1 | 1 | 0
94 | Rig Up | Rig Site | RESERVE MUD TANK-2 | Priority 2 | LOW BED | 98 ¦ 93 | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 1 | 1 | 0
95 | Rig Down | Rig Site | TREATMENT TANK/DEGASSER TANK | Priority 2 | LOW BED | None | 12 Hrs ± 1 Hr (System Total) | Yes | 1 | 2 | 0 | 0 | 0
96 | Rig Up | Rig Site | TREATMENT TANK/DEGASSER TANK | Priority 2 | LOW BED | 98 ¦ 95 | 20 Hrs ± 2 Hrs (System Total) | Yes | 1 | 2 | 0 | 0 | 0
97 | Rig Down | Rig Site | RIG WATER TANK + HOPPERS | Priority 2 | LOW BED | None | 2 Hrs ± 0.5 Hrs (System Total) | Yes | 2 | 4 | 0 | 0 | 0
98 | Rig Up | Rig Site | RIG WATER TANK + HOPPERS | Priority 2 | LOW BED | 97 | 20 Hrs ± 2 Hrs (System Total) | Yes | 2 | 4 | 0 | 0 | 0
99 | Rig Down | Rig Site | SPARE MUD TANK (BLUE) | Priority 2 | LOW BED | None | 12 Hrs ± 1 Hr (System Total) | No | 2 | 4 | 1 | 1 | 0
100 | Rig Up | Rig Site | SPARE MUD TANK (BLUE) | Priority 2 | LOW BED | 98 ¦ 99 | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 1 | 1 | 0
101 | Rig Down | Rig Site | PCR (Power Control Room) | Priority 2 | LOW BED | None | Not Specified | Yes | 1 | 2 | 2 | 0 | 0
102 | Rig Up | Rig Site | PCR (Power Control Room) | Priority 2 | LOW BED | 101 | Not Specified | Yes | 1 | 2 | 2 | 0 | 0
103 | Rig Down | Rig Site | MUD PUMP-1 | Priority 2 | LOW BED | 87 | 2 Hrs ± 0.5 Hrs | Yes | 3 | 2 | 0 | 2 | 0
104 | Rig Up | Rig Site | MUD PUMP-1 | Priority 2 | LOW BED | 88 ¦ 103 | 3 Hrs ± 0.5 Hrs | Yes | 3 | 2 | 0 | 2 | 0
105 | Rig Down | Rig Site | MUD PUM-2 | Priority 2 | LOW BED | 87 | 2 Hrs ± 0.5 Hrs | Yes | 1 | 2 | 0 | 0 | 0
106 | Rig Up | Rig Site | MUD PUM-2 | Priority 2 | LOW BED | 88 ¦ 105 | 3 Hrs ± 0.5 Hrs | Yes | 1 | 2 | 0 | 0 | 0
107 | Rig Down | Rig Site | TRIP TANK SKID | Priority 2 | LOW BED | None | 12 Hrs ± 1 Hr (System Total) | Yes | 1 | 2 | 0 | 0 | 0
108 | Rig Up | Rig Site | TRIP TANK SKID | Priority 2 | LOW BED | 98 ¦ 107 | 20 Hrs ± 2 Hrs (System Total) | Yes | 1 | 2 | 0 | 0 | 0
109 | Rig Down | Rig Site | SHAKER SKID | Priority 2 | LOW BED | None | 12 Hrs ± 1 Hr (System Total) | Yes | 2 | 4 | 0 | 0 | 0
110 | Rig Up | Rig Site | SHAKER SKID | Priority 2 | LOW BED | 98 ¦ 109 | 20 Hrs ± 2 Hrs (System Total) | Yes | 2 | 4 | 0 | 0 | 0
111 | Rig Down | Rig Site | SHAKER SKID WALK WAY-RIGHT | Priority 2 | LOW BED | None | 12 Hrs ± 1 Hr (System Total) | No | 2 | 4 | 0 | 0 | 0
112 | Rig Up | Rig Site | SHAKER SKID WALK WAY-RIGHT | Priority 2 | LOW BED | 98 ¦ 111 | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 0 | 0 | 0
113 | Rig Down | Rig Site | SHAKER SKID WALKWAY - LEFT | Priority 2 | LOW BED | None | 12 Hrs ± 1 Hr (System Total) | No | 2 | 4 | 0 | 0 | 0
114 | Rig Up | Rig Site | SHAKER SKID WALKWAY - LEFT | Priority 2 | LOW BED | 98 ¦ 113 | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 0 | 0 | 0
115 | Rig Down | Rig Site | RIG ENGINE # 1 | Priority 2 | LOW BED | None | 10 Hrs ± 1 Hr (System Total) | Yes | 3 | 2 | 0 | 2 | 0
116 | Rig Up | Rig Site | RIG ENGINE # 1 | Priority 2 | LOW BED | 102 ¦ 115 | 5 Hrs ± 1 Hr (System Total) | Yes | 3 | 2 | 0 | 2 | 0
117 | Rig Down | Rig Site | RIG ENGINE # 2 | Priority 2 | LOW BED | None | 10 Hrs ± 1 Hr (System Total) | Yes | 3 | 2 | 0 | 2 | 0
118 | Rig Up | Rig Site | RIG ENGINE # 2 | Priority 2 | LOW BED | 102 ¦ 117 | 5 Hrs ± 1 Hr (System Total) | Yes | 3 | 2 | 0 | 2 | 0
119 | Rig Down | Rig Site | RIG ENGINE # 3 | Priority 2 | LOW BED | None | 10 Hrs ± 1 Hr (System Total) | Yes | 3 | 2 | 0 | 2 | 0
120 | Rig Up | Rig Site | RIG ENGINE # 3 | Priority 2 | LOW BED | 102 ¦ 119 | 5 Hrs ± 1 Hr (System Total) | Yes | 3 | 2 | 0 | 2 | 0
121 | Rig Down | Rig Site | KOOMY SKID (Accumulator) | Priority 2 | LOW BED | None | 4 Hrs ± 0.5 Hrs | Yes | 1 | 2 | 0 | 1 | 0
122 | Rig Up | Rig Site | KOOMY SKID (Accumulator) | Priority 2 | LOW BED | 121 | 5 Hrs ± 0.5 Hrs | Yes | 1 | 2 | 0 | 1 | 0
123 | Rig Down | Rig Site | DRAWORKS | Priority 2 | LOW BED | 65 | 1 Hr ± 0.25 Hrs | Yes | 1 | 2 | 0 | 0 | 0
124 | Rig Up | Rig Site | DRAWORKS | Priority 2 | LOW BED | 76 ¦ 123 | 2.5 Hrs ± 0.5 Hrs | Yes | 1 | 2 | 0 | 0 | 0
125 | Rig Down | Rig Site | WHITE WATER TANK + GROUND HOPPER | Priority 2 | FLAT BED | None | 2 Hrs ± 0.5 Hrs (System Total) | No | 2 | 4 | 0 | 0 | 0
126 | Rig Up | Rig Site | WHITE WATER TANK + GROUND HOPPER | Priority 2 | FLAT BED | 125 | 20 Hrs ± 2 Hrs (System Total) | No | 2 | 4 | 0 | 0 | 0
127 | Rig Down | Rig Site | GROSS HOPPER | Priority 2 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 0
128 | Rig Up | Rig Site | GROSS HOPPER | Priority 2 | FLAT BED | 124 ¦ 127 | Not Specified | No | 1 | 2 | 0 | 0 | 0
129 | Rig Down | Rig Site | COOLING SKID | Priority 2 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 0
130 | Rig Up | Rig Site | COOLING SKID | Priority 2 | FLAT BED | 98 ¦ 129 | Not Specified | No | 1 | 2 | 0 | 0 | 0
131 | Rig Down | Rig Site | FLARE LINES / RACKS | Priority 2 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 1
132 | Rig Up | Rig Site | FLARE LINES / RACKS | Priority 2 | FLAT BED | 124 ¦ 131 | Not Specified | No | 1 | 2 | 0 | 0 | 1
133 | Rig Down | Rig Site | Drill Pipe set back & Rotary table beams | Priority 2 | FLAT BED | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
134 | Rig Up | Rig Site | Drill Pipe set back & Rotary table beams | Priority 2 | FLAT BED | 124 ¦ 133 | Not Specified | No | 2 | 4 | 0 | 0 | 0
135 | Rig Down | Rig Site | X-OVER BASKET | Priority 2 | FLAT BED | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
136 | Rig Up | Rig Site | X-OVER BASKET | Priority 2 | FLAT BED | 124 ¦ 135 | Not Specified | No | 2 | 4 | 0 | 0 | 0
137 | Rig Down | Rig Site | CATWALK / MOUSE HOLE | Priority 2 | FLAT BED | None | Not Specified | Yes | 2 | 4 | 0 | 0 | 0
138 | Rig Up | Rig Site | CATWALK / MOUSE HOLE | Priority 2 | FLAT BED | 124 ¦ 137 | Not Specified | Yes | 2 | 4 | 0 | 0 | 0
139 | Rig Down | Rig Site | RIG TOILET + SULAIR COMPRESSOR | Priority 2 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 1 | 0
140 | Rig Up | Rig Site | RIG TOILET + SULAIR COMPRESSOR | Priority 2 | FLAT BED | 139 | Not Specified | No | 1 | 2 | 0 | 1 | 0
141 | Rig Down | Rig Site | OIL BASKET | Priority 2 | FLAT BED | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
142 | Rig Up | Rig Site | OIL BASKET | Priority 2 | FLAT BED | 141 | Not Specified | No | 2 | 4 | 0 | 0 | 0
143 | Rig Down | Rig Site | MECHANICAL BASKET | Priority 2 | FLAT BED | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
144 | Rig Up | Rig Site | MECHANICAL BASKET | Priority 2 | FLAT BED | 143 | Not Specified | No | 2 | 4 | 0 | 0 | 0
145 | Rig Down | Rig Site | ELECTRIC BASKET | Priority 2 | FLAT BED | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
146 | Rig Up | Rig Site | ELECTRIC BASKET | Priority 2 | FLAT BED | 145 | Not Specified | No | 2 | 4 | 0 | 0 | 0
147 | Rig Down | Rig Site | TRAINING ROOM | Priority 2 | FLAT BED | None | Not Specified | No | 1 | 2 | 1 | 0 | 0
148 | Rig Up | Rig Site | TRAINING ROOM | Priority 2 | FLAT BED | 147 | Not Specified | No | 1 | 2 | 1 | 0 | 0
149 | Rig Down | Rig Site | DIESEL TANK -1 | Priority 2 | LOW BED | None | 5 Hrs ± 1 Hr (System Total) | Yes | 1 | 2 | 0 | 0 | 0
150 | Rig Up | Rig Site | DIESEL TANK -1 | Priority 2 | LOW BED | 149 | 5 Hrs ± 1 Hr (System Total) | Yes | 1 | 2 | 0 | 0 | 0
151 | Rig Down | Rig Site | DIESEL TANK-2 | Priority 2 | LOW BED | None | 5 Hrs ± 1 Hr (System Total) | No | 1 | 2 | 0 | 0 | 0
152 | Rig Up | Rig Site | DIESEL TANK-2 | Priority 2 | LOW BED | 151 | 5 Hrs ± 1 Hr (System Total) | No | 1 | 2 | 0 | 0 | 0
153 | Rig Down | Rig Site | CSG HANDLING DSA BASKET | Priority 2 | LOW BED | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
154 | Rig Up | Rig Site | CSG HANDLING DSA BASKET | Priority 2 | LOW BED | 153 | Not Specified | No | 2 | 4 | 0 | 0 | 0
155 | Rig Down | Rig Site | BOP SKID STUMP 13 5/8" | Priority 2 | LOW BED | None | Not Specified | Yes | 3 | 2 | 0 | 0 | 0
156 | Rig Up | Rig Site | BOP SKID STUMP 13 5/8" | Priority 2 | LOW BED | 124 ¦ 155 | Not Specified | Yes | 3 | 2 | 0 | 0 | 0
157 | Rig Down | Rig Site | SUPER CHARGER SKID | Priority 2 | LOW BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 0
158 | Rig Up | Rig Site | SUPER CHARGER SKID | Priority 2 | LOW BED | 88 ¦ 157 | Not Specified | No | 1 | 2 | 0 | 0 | 0
159 | Rig Down | Rig Site | DRILLER SHELTER/HYD UNIT | Priority 2 | LOW BED | None | Not Specified | Yes | 1 | 2 | 0 | 0 | 0
160 | Rig Up | Rig Site | DRILLER SHELTER/HYD UNIT | Priority 2 | LOW BED | 124 ¦ 159 | Not Specified | Yes | 1 | 2 | 0 | 0 | 0
161 | Rig Down | Rig Site | POOR BOY DEGASSER/CHOKEMANIFOLD | Priority 2 | LOW BED | None | 2 Hrs ± 0.5 Hrs | Yes | 3 | 2 | 0 | 0 | 0
162 | Rig Up | Rig Site | POOR BOY DEGASSER/CHOKEMANIFOLD | Priority 2 | LOW BED | 88 ¦ 161 | Not Specified | Yes | 3 | 2 | 0 | 0 | 0
163 | Rig Down | Rig Site | DRILL COLLAR BASKET 4 3/4" | Priority 2 | HEAVY HAULER | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
164 | Rig Up | Rig Site | DRILL COLLAR BASKET 4 3/4" | Priority 2 | HEAVY HAULER | 124 ¦ 163 | Not Specified | No | 2 | 4 | 0 | 0 | 0
165 | Rig Down | Rig Site | 3 1/2" DRILL PIPE BASKET #1(G-11) | Priority 2 | HEAVY HAULER | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
166 | Rig Up | Rig Site | 3 1/2" DRILL PIPE BASKET #1(G-11) | Priority 2 | HEAVY HAULER | 124 ¦ 165 | Not Specified | No | 2 | 4 | 0 | 0 | 0
167 | Rig Down | Rig Site | 3 1/2" DRILL PIPE BASKET #2 (G-11) | Priority 2 | HEAVY HAULER | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
168 | Rig Up | Rig Site | 3 1/2" DRILL PIPE BASKET #2 (G-11) | Priority 2 | HEAVY HAULER | 124 ¦ 167 | Not Specified | No | 2 | 4 | 0 | 0 | 0
169 | Rig Down | Rig Site | 3 1/2" DRILL PIPE BASKET #3(G-11) | Priority 2 | HEAVY HAULER | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
170 | Rig Up | Rig Site | 3 1/2" DRILL PIPE BASKET #3(G-11) | Priority 2 | HEAVY HAULER | 124 ¦ 169 | Not Specified | No | 2 | 4 | 0 | 0 | 0
171 | Rig Down | Rig Site | 3 1/2" DRILL PIPE BASKET #4 (G-111) | Priority 2 | HEAVY HAULER | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
172 | Rig Up | Rig Site | 3 1/2" DRILL PIPE BASKET #4 (G-111) | Priority 2 | HEAVY HAULER | 124 ¦ 171 | Not Specified | No | 2 | 4 | 0 | 0 | 0
173 | Rig Down | Rig Site | 3 1/2" DRILL PIPE BASEKT #5 (S-135) | Priority 2 | HEAVY HAULER | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
174 | Rig Up | Rig Site | 3 1/2" DRILL PIPE BASEKT #5 (S-135) | Priority 2 | HEAVY HAULER | 124 ¦ 173 | Not Specified | No | 2 | 4 | 0 | 0 | 0
175 | Rig Down | Rig Site | NO CHARGE STORE | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 0
176 | Rig Up | Rig Site | NO CHARGE STORE | Priority 3 | FLAT BED | 175 | Not Specified | No | 1 | 2 | 0 | 0 | 0
177 | Rig Down | Rig Site | RUBBER STORE | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 0
178 | Rig Up | Rig Site | RUBBER STORE | Priority 3 | FLAT BED | 177 | Not Specified | No | 1 | 2 | 0 | 0 | 0
179 | Rig Down | Rig Site | FISHING STORE | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 0
180 | Rig Up | Rig Site | FISHING STORE | Priority 3 | FLAT BED | 179 | Not Specified | No | 1 | 2 | 0 | 0 | 0
181 | Rig Down | Rig Site | DRILLING STORE | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 0
182 | Rig Up | Rig Site | DRILLING STORE | Priority 3 | FLAT BED | 181 | Not Specified | No | 1 | 2 | 0 | 0 | 0
183 | Rig Down | Rig Site | ELECTRIC STORE | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 0
184 | Rig Up | Rig Site | ELECTRIC STORE | Priority 3 | FLAT BED | 183 | Not Specified | No | 1 | 2 | 0 | 0 | 0
185 | Rig Down | Rig Site | MECHANICAL STORE | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 0
186 | Rig Up | Rig Site | MECHANICAL STORE | Priority 3 | FLAT BED | 185 | Not Specified | No | 1 | 2 | 0 | 0 | 0
187 | Rig Down | Rig Site | WELDING SHOP | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 1
188 | Rig Up | Rig Site | WELDING SHOP | Priority 3 | FLAT BED | 187 | Not Specified | No | 1 | 2 | 0 | 0 | 1
189 | Rig Down | Rig Site | PAINT STORE / BOP STORE | Priority 3 | FLAT BED | None | Not Specified | No | 3 | 2 | 0 | 0 | 0
190 | Rig Up | Rig Site | PAINT STORE / BOP STORE | Priority 3 | FLAT BED | 189 | Not Specified | No | 3 | 2 | 0 | 0 | 0
191 | Rig Down | Rig Site | MECHANICAL/ELECTRIC WORKSHOP | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 0
192 | Rig Up | Rig Site | MECHANICAL/ELECTRIC WORKSHOP | Priority 3 | FLAT BED | 191 | Not Specified | No | 1 | 2 | 0 | 0 | 0
193 | Rig Down | Rig Site | PMS OFFICE | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 4 | 1 | 0 | 0
194 | Rig Up | Rig Site | PMS OFFICE | Priority 3 | FLAT BED | 193 | Not Specified | No | 1 | 4 | 1 | 0 | 0
195 | Rig Down | Rig Site | TOOL PUSHER OFFICE | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 4 | 1 | 0 | 0
196 | Rig Up | Rig Site | TOOL PUSHER OFFICE | Priority 3 | FLAT BED | 195 | Not Specified | No | 1 | 4 | 1 | 0 | 0
197 | Rig Down | Rig Site | COMPANY MAN OFFICE | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 4 | 1 | 0 | 0
198 | Rig Up | Rig Site | COMPANY MAN OFFICE | Priority 3 | FLAT BED | 197 | Not Specified | No | 1 | 4 | 1 | 0 | 0
199 | Rig Down | Rig Site | CLINIC | Priority 3 | FLAT BED | None | Not Specified | Yes | 1 | 2 | 1 | 0 | 1
200 | Rig Up | Rig Site | CLINIC | Priority 3 | FLAT BED | 199 | Not Specified | Yes | 1 | 2 | 1 | 0 | 1
201 | Rig Down | Rig Site | MIC LIVING / RIG MANAGER CARAVAN | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 4 | 1 | 0 | 0
202 | Rig Up | Rig Site | MIC LIVING / RIG MANAGER CARAVAN | Priority 3 | FLAT BED | 201 | Not Specified | No | 1 | 4 | 1 | 0 | 0
203 | Rig Down | Rig Site | GEOLOGIST ROOM/RADIO ROOM | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 2 | 1 | 0 | 0
204 | Rig Up | Rig Site | GEOLOGIST ROOM/RADIO ROOM | Priority 3 | FLAT BED | 203 | Not Specified | No | 1 | 2 | 1 | 0 | 0
205 | Rig Down | Rig Site | WATER TANKS RIG CAMP | Priority 3 | FLAT BED | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
206 | Rig Up | Rig Site | WATER TANKS RIG CAMP | Priority 3 | FLAT BED | 205 | Not Specified | No | 2 | 4 | 0 | 0 | 0
207 | Rig Down | Rig Site | KOOMY LINES / LADERS | Priority 3 | FLAT BED | None | Not Specified | Yes | 1 | 2 | 0 | 1 | 0
208 | Rig Up | Rig Site | KOOMY LINES / LADERS | Priority 3 | FLAT BED | 207 | Not Specified | Yes | 1 | 2 | 0 | 1 | 0
209 | Rig Down | Rig Site | WELDERS BASKET | Priority 3 | FLAT BED | None | Not Specified | No | 2 | 4 | 0 | 0 | 0
210 | Rig Up | Rig Site | WELDERS BASKET | Priority 3 | FLAT BED | 209 | Not Specified | No | 2 | 4 | 0 | 0 | 0
211 | Rig Down | Rig Site | SAFETY CONTAINER | Priority 3 | FLAT BED | None | Not Specified | No | 1 | 2 | 0 | 0 | 1
212 | Rig Up | Rig Site | SAFETY CONTAINER | Priority 3 | FLAT BED | 211 | Not Specified | No | 1 | 2 | 0 | 0 | 1

## Sheet1
ID | Phase | Task Description | Pred 1 (Assembly) | Pred 2 (Logistics) | Weight (Tons) | Required Lifting Resource | Minimum Crew Requirement (number and name) | Avg Duration (hrs) + var | Truck Type | Optimal Crew Requirement (number and name) | Avg Duration (hrs) + var | Critical Lift? | Priority
1 | vbc | Safety Meeting & Work Permit | 0 | 0 | 0 |  |  |  | N/A
2 | Rig Down | Nipple Down BOP Stack | 1 | 0 | 0 |  |  |  | N/A
3 | Rig Down | Disconnect Choke Manifold | 2 | 0 | 12 |  |  |  | Flatbed
4 | Rig Down | Disconnect Koomey Unit | 2 | 0 | 15 |  |  |  | Bed Truck
5 | Rig Down | Spool Drill Line | 1 | 0 | 8 |  |  |  | Flatbed
6 | Rig Down | Remove Flow Line | 2 | 0 | 4 |  |  |  | Flatbed
7 | Rig Down | Camp: Disconnect Water/Power | 1 | 0 | 0 |  |  |  | N/A
8 | Rig Down | Load Camp: Rig Manager Office | 7 | 0 | 18 |  |  |  | Lowboy (Wide)
9 | Rig Down | Load Camp: Company Man Office | 7 | 0 | 18 |  |  |  | Lowboy (Wide)
10 | Rig Down | Load Camp: Kitchen Unit | 7 | 0 | 20 |  |  |  | Lowboy (Wide)
11 | Rig Down | Load Camp: Diner Unit | 7 | 0 | 18 |  |  |  | Lowboy (Wide)
12 | Rig Down | Load Camp: Sleeper 1 (Senior) | 7 | 0 | 18 |  |  |  | Lowboy (Wide)
13 | Rig Down | Load Camp: Sleeper 2 (Senior) | 7 | 0 | 18 |  |  |  | Lowboy (Wide)
14 | Rig Down | Load Camp: Sleeper 3 (Junior) | 7 | 0 | 18 |  |  |  | Lowboy (Wide)
15 | Rig Down | Load Camp: Sleeper 4 (Junior) | 7 | 0 | 18 |  |  |  | Lowboy (Wide)
16 | Rig Down | Load Camp: Laundry Unit | 7 | 0 | 15 |  |  |  | Lowboy (Wide)
17 | Rig Down | Load Camp: Clinic/Safety | 7 | 0 | 15 |  |  |  | Lowboy (Wide)
18 | Rig Down | Load Camp: Prayer Room | 7 | 0 | 12 |  |  |  | Lowboy (Wide)
19 | Rig Down | Load Camp: Generator A | 7 | 0 | 25 |  |  |  | Flatbed
20 | Rig Down | Load Camp: Generator B | 7 | 0 | 25 |  |  |  | Flatbed
21 | Rig Down | Load Camp: Water Tank 1 | 7 | 0 | 10 |  |  |  | Bed Truck
22 | Rig Down | Load Camp: Water Tank 2 | 7 | 0 | 10 |  |  |  | Bed Truck
23 | Rig Down | Load Camp: Sewage Tank | 7 | 0 | 12 |  |  |  | Bed Truck
24 | Rig Down | Load Camp: Fuel Tank | 7 | 0 | 12 |  |  |  | Bed Truck
25 | Rig Down | Load Camp: Garbage Skip | 7 | 0 | 5 |  |  |  | Flatbed
26 | Rig Down | Load Pipe Bin 1 (Drill Pipe) | 1 | 0 | 18 |  |  |  | Bed Truck
27 | Rig Down | Load Pipe Bin 2 (Drill Pipe) | 26 | 0 | 18 |  |  |  | Bed Truck
28 | Rig Down | Load Pipe Bin 3 (Drill Pipe) | 27 | 0 | 18 |  |  |  | Bed Truck
29 | Rig Down | Load Pipe Bin 4 (Drill Pipe) | 28 | 0 | 18 |  |  |  | Bed Truck
30 | Rig Down | Load Pipe Bin 5 (Drill Pipe) | 29 | 0 | 18 |  |  |  | Bed Truck
31 | Rig Down | Load Pipe Bin 6 (Drill Pipe) | 30 | 0 | 18 |  |  |  | Bed Truck
32 | Rig Down | Load Pipe Bin 7 (HWDP) | 31 | 0 | 18 |  |  |  | Bed Truck
33 | Rig Down | Load Pipe Bin 8 (Collars) | 32 | 0 | 20 |  |  |  | Bed Truck
34 | Rig Down | Load Pipe Bin 9 (Casing) | 33 | 0 | 22 |  |  |  | Bed Truck
35 | Rig Down | Load Pipe Bin 10 (Casing) | 34 | 0 | 22 |  |  |  | Bed Truck
36 | Rig Down | Clean & Load Mud Tank 1 (Res) | 1 | 0 | 22 |  |  |  | Flatbed
37 | Rig Down | Clean & Load Mud Tank 2 (Res) | 36 | 0 | 22 |  |  |  | Flatbed
38 | Rig Down | Clean & Load Mud Tank 3 (Mix) | 37 | 0 | 24 |  |  |  | Flatbed
39 | Rig Down | Clean & Load Mud Tank 4 (Suc) | 38 | 0 | 24 |  |  |  | Flatbed
40 | Rig Down | Load Pill Tank / Trip Tank | 39 | 0 | 15 |  |  |  | Bed Truck
41 | Rig Down | Disconnect Mud Pump 1 | 39 | 0 | 42 |  |  |  | Lowboy (Heavy)
42 | Rig Down | Disconnect Mud Pump 2 | 41 | 0 | 42 |  |  |  | Lowboy (Heavy)
43 | Rig Down | Disconnect Mud Pump 3 | 42 | 0 | 42 |  |  |  | Lowboy (Heavy)
44 | Rig Down | Load High Pressure Lines | 43 | 0 | 12 |  |  |  | Flatbed
45 | Rig Down | Load Cable Trays (Power) | 40 | 0 | 8 |  |  |  | Flatbed
46 | Rig Down | Load PCR / VFD House | 45 | 0 | 35 |  |  |  | Lowboy (Wide)
47 | Rig Down | Load Generator 1 | 46 | 0 | 32 |  |  |  | Lowboy
48 | Rig Down | Load Generator 2 | 47 | 0 | 32 |  |  |  | Lowboy
49 | Rig Down | Load Generator 3 | 48 | 0 | 32 |  |  |  | Lowboy
50 | Rig Down | Load Generator 4 | 49 | 0 | 32 |  |  |  | Lowboy
51 | Rig Down | Load Fuel Tank 1 | 50 | 0 | 15 |  |  |  | Bed Truck
52 | Rig Down | Load Fuel Tank 2 | 51 | 0 | 15 |  |  |  | Bed Truck
53 | Rig Down | Load Water Tank 1 | 50 | 0 | 12 |  |  |  | Bed Truck
54 | Rig Down | Load Water Tank 2 | 53 | 0 | 12 |  |  |  | Bed Truck
55 | Rig Down | Lower Mast (Jack Down) | 2 | 0 | 0 |  |  |  | N/A
56 | Rig Down | Remove Top Drive / Block | 55 | 0 | 20 |  |  |  | Lowboy
57 | Rig Down | Disassemble Mast Sec 1 (Top) | 56 | 0 | 18 |  |  |  | Lowboy (Wide)
58 | Rig Down | Disassemble Mast Sec 2 | 57 | 0 | 18 |  |  |  | Lowboy (Wide)
59 | Rig Down | Disassemble Mast Sec 3 | 58 | 0 | 18 |  |  |  | Lowboy (Wide)
60 | Rig Down | Disassemble Mast Sec 4 (Base) | 59 | 0 | 22 |  |  |  | Lowboy (Wide)
61 | Rig Down | Load Racking Board | 57 | 0 | 10 |  |  |  | Flatbed
62 | Rig Down | Load Monkey Board | 57 | 0 | 8 |  |  |  | Flatbed
63 | Rig Down | Load Standpipe Manifold | 60 | 0 | 12 |  |  |  | Flatbed
64 | Rig Down | Remove Doghouse (Cabin) | 55 | 0 | 15 |  |  |  | Bed Truck
65 | Rig Down | Remove Driller Console | 64 | 0 | 5 |  |  |  | Flatbed
66 | Rig Down | Remove Rotary Table | 55 | 0 | 12 |  |  |  | Bed Truck
67 | Rig Down | Remove Drawworks (Main) | 55 | 0 | 48 |  |  |  | Multi-Axle
68 | Rig Down | Remove Drawworks Motors | 67 | 0 | 15 |  |  |  | Flatbed
69 | Rig Down | Remove Catwalks | 55 | 0 | 8 |  |  |  | Bed Truck
70 | Rig Down | Remove Pipe Racks (Set 1) | 69 | 0 | 12 |  |  |  | Flatbed
71 | Rig Down | Remove Pipe Racks (Set 2) | 70 | 0 | 12 |  |  |  | Flatbed
72 | Rig Down | Disassemble Substructure 1 | 67 | 0 | 38 |  |  |  | Lowboy (Heavy)
73 | Rig Down | Disassemble Substructure 2 | 72 | 0 | 38 |  |  |  | Lowboy (Heavy)
74 | Rig Down | Disassemble Substructure 3 | 73 | 0 | 38 |  |  |  | Lowboy (Heavy)
75 | Rig Down | Load Sub-Base Beam A | 74 | 0 | 15 |  |  |  | Flatbed
76 | Rig Down | Load Sub-Base Beam B | 75 | 0 | 15 |  |  |  | Flatbed
77 | Rig Down | Load BOP Handling Skid | 74 | 0 | 10 |  |  |  | Flatbed
78 | Rig Down | Load Workshop Container | 45 | 0 | 18 |  |  |  | Bed Truck
79 | Rig Down | Load Parts Container | 45 | 0 | 18 |  |  |  | Bed Truck
80 | Rig Down | Load Electrical Shop | 45 | 0 | 18 |  |  |  | Bed Truck
81 | Rig Down | Load Welding Shop | 45 | 0 | 18 |  |  |  | Bed Truck
82 | Rig Down | Load Junk Basket / Skips | 81 | 0 | 10 |  |  |  | Flatbed
83 | Rig Down | Load Centrifuges | 39 | 0 | 12 |  |  |  | Flatbed
84 | Rig Down | Load Degasser Unit | 39 | 0 | 8 |  |  |  | Flatbed
85 | Rig Down | Load Shakers (1 & 2) | 39 | 0 | 15 |  |  |  | Flatbed
86 | Rig Down | Load Cement Unit (Third Party) | 1 | 0 | 25 |  |  |  | Bed Truck
87 | Rig Down | Load Wireline Unit (Third Party) | 1 | 0 | 20 |  |  |  | Bed Truck
88 | Rig Down | Load Chemical Pallets | 39 | 0 | 15 |  |  |  | Flatbed
89 | Rig Down | Load Barite Bulk Tank | 39 | 0 | 15 |  |  |  | Bed Truck
90 | Rig Down | Load Bentonite Bulk Tank | 39 | 0 | 15 |  |  |  | Bed Truck
91 | Rig Down | Demobilize Forklift | 82 | 0 | 8 |  |  |  | Flatbed
92 | Rig Down | Demobilize Loader | 82 | 0 | 18 |  |  |  | Lowboy
93 | Rig Down | Demobilize Small Crane | 82 | 0 | 25 |  |  |  | Lowboy
94 | Rig Down | Load Site Lighting Towers | 50 | 0 | 5 |  |  |  | Flatbed
95 | Rig Down | Load Fire Pumps | 50 | 0 | 5 |  |  |  | Flatbed
96 | Rig Down | Clean Cellar (Site A) | 2 | 0 | 0 |  |  |  | N/A
97 | Rig Down | Install Wellhead Cap | 2 | 0 | 0 |  |  |  | N/A
98 | Rig Down | Final Site Cleanup (Scrap) | 97 | 0 | 10 |  |  |  | Dump Truck
99 | Rig Down | Site Inspection & Handover | 98 | 0 | 0 |  |  |  | N/A
100 | Rig Down | Release Convoy to Site B | 99 | 0 | 0 |  |  |  | N/A
101 | Rig Up | Survey & Stake Location | 0 | 0 | 0 |  |  |  | N/A
102 | Rig Up | Civil Works: Level Pads | 101 | 0 | 0 |  |  |  | Grader
103 | Rig Up | Civil Works: Dig Cellar | 102 | 0 | 0 |  |  |  | Excavator
104 | Rig Up | Lay Rig Mats (Foundation) | 102 | 0 | 15 |  |  |  | Flatbed
105 | Rig Up | Spot Camp: Rig Manager | 104 | 8 | 18 |  |  |  | Lowboy (Wide)
106 | Rig Up | Spot Camp: Company Man | 104 | 9 | 18 |  |  |  | Lowboy (Wide)
107 | Rig Up | Spot Camp: Kitchen | 104 | 10 | 20 |  |  |  | Lowboy (Wide)
108 | Rig Up | Spot Camp: Diner | 107 | 11 | 18 |  |  |  | Lowboy (Wide)
109 | Rig Up | Spot Camp: Sleepers 1-4 | 105 | 12 | 18 |  |  |  | Lowboy (Wide)
110 | Rig Up | Spot Camp: Laundry/Clinic | 109 | 16 | 15 |  |  |  | Lowboy (Wide)
111 | Rig Up | Spot Camp Generator A | 109 | 19 | 25 |  |  |  | Flatbed
112 | Rig Up | Connect Camp Power/Water | 111 | 21 | 0 |  |  |  | N/A
113 | Rig Up | Spot Sub-Base Beams | 104 | 75 | 15 |  |  |  | Flatbed
114 | Rig Up | Assemble Substructure 1 | 113 | 72 | 38 |  |  |  | Lowboy (Heavy)
115 | Rig Up | Assemble Substructure 2 | 114 | 73 | 38 |  |  |  | Lowboy (Heavy)
116 | Rig Up | Assemble Substructure 3 | 115 | 74 | 38 |  |  |  | Lowboy (Heavy)
117 | Rig Up | Level & Pin Substructure | 116 | 0 | 0 |  |  |  | N/A
118 | Rig Up | Spot Drawworks (Main) | 117 | 67 | 48 |  |  |  | Multi-Axle
119 | Rig Up | Install Drawworks Motors | 118 | 68 | 15 |  |  |  | Flatbed
120 | Rig Up | Spot Rotary Table | 117 | 66 | 12 |  |  |  | Bed Truck
121 | Rig Up | Install Catwalks & V-Door | 117 | 69 | 8 |  |  |  | Bed Truck
122 | Rig Up | Spot Pipe Racks | 121 | 70 | 12 |  |  |  | Flatbed
123 | Rig Up | Install Doghouse (Cabin) | 117 | 64 | 15 |  |  |  | Bed Truck
124 | Rig Up | Install Driller Console | 123 | 65 | 5 |  |  |  | Flatbed
125 | Rig Up | Spot Mast Sec 4 (Base) | 117 | 60 | 22 |  |  |  | Lowboy (Wide)
126 | Rig Up | Pin Mast Sec 3 | 125 | 59 | 18 |  |  |  | Lowboy (Wide)
127 | Rig Up | Pin Mast Sec 2 | 126 | 58 | 18 |  |  |  | Lowboy (Wide)
128 | Rig Up | Pin Mast Sec 1 (Top) | 127 | 57 | 18 |  |  |  | Lowboy (Wide)
129 | Rig Up | Install Crown & Top Drive | 128 | 56 | 20 |  |  |  | Lowboy
130 | Rig Up | Install Racking Board | 127 | 61 | 10 |  |  |  | Flatbed
131 | Rig Up | Install Standpipe Manifold | 125 | 63 | 12 |  |  |  | Flatbed
132 | Rig Up | Reeve Drill Line (String up) | 129 | 5 | 0 |  |  |  | N/A
133 | Rig Up | Raise Mast (Jack Up) | 132 | 0 | 0 |  |  |  | N/A
134 | Rig Up | Spot PCR / VFD House | 104 | 46 | 35 |  |  |  | Lowboy (Wide)
135 | Rig Up | Spot Generator 1 | 134 | 47 | 32 |  |  |  | Lowboy
136 | Rig Up | Spot Generator 2 | 135 | 48 | 32 |  |  |  | Lowboy
137 | Rig Up | Spot Generator 3 | 136 | 49 | 32 |  |  |  | Lowboy
138 | Rig Up | Spot Generator 4 | 137 | 50 | 32 |  |  |  | Lowboy
139 | Rig Up | Spot Fuel Tanks | 135 | 51 | 15 |  |  |  | Bed Truck
140 | Rig Up | Install Cable Trays (Power) | 138 | 45 | 8 |  |  |  | Flatbed
141 | Rig Up | Connect High Voltage Lines | 140 | 0 | 0 |  |  |  | N/A
142 | Rig Up | Spot Mud Tank 1 (Res) | 104 | 36 | 22 |  |  |  | Flatbed
143 | Rig Up | Spot Mud Tank 2 (Res) | 142 | 37 | 22 |  |  |  | Flatbed
144 | Rig Up | Spot Mud Tank 3 (Mix) | 143 | 38 | 24 |  |  |  | Flatbed
145 | Rig Up | Spot Mud Tank 4 (Suc) | 144 | 39 | 24 |  |  |  | Flatbed
146 | Rig Up | Install Tank Walkways | 145 | 0 | 5 |  |  |  | Flatbed
147 | Rig Up | Spot Mud Pump 1 | 145 | 41 | 42 |  |  |  | Lowboy (Heavy)
148 | Rig Up | Spot Mud Pump 2 | 147 | 42 | 42 |  |  |  | Lowboy (Heavy)
149 | Rig Up | Spot Mud Pump 3 | 148 | 43 | 42 |  |  |  | Lowboy (Heavy)
150 | Rig Up | Install High Pressure Lines | 149 | 44 | 12 |  |  |  | Flatbed
151 | Rig Up | Install Shakers | 145 | 85 | 15 |  |  |  | Flatbed
152 | Rig Up | Install Degasser / Centrifuge | 145 | 83 | 12 |  |  |  | Flatbed
153 | Rig Up | Spot Water Tanks (Rig) | 145 | 53 | 12 |  |  |  | Bed Truck
154 | Rig Up | Spot Barite/Bentonite Silos | 145 | 89 | 15 |  |  |  | Bed Truck
155 | Rig Up | Spot Workshop Container | 104 | 78 | 18 |  |  |  | Bed Truck
156 | Rig Up | Spot Parts Container | 104 | 79 | 18 |  |  |  | Bed Truck
157 | Rig Up | Spot Electrical Shop | 104 | 80 | 18 |  |  |  | Bed Truck
158 | Rig Up | Spot Welding Shop | 104 | 81 | 18 |  |  |  | Bed Truck
159 | Rig Up | Spot Pipe Bin 1 | 122 | 26 | 18 |  |  |  | Bed Truck
160 | Rig Up | Spot Pipe Bin 2 | 159 | 27 | 18 |  |  |  | Bed Truck
161 | Rig Up | Spot Pipe Bin 3 | 160 | 28 | 18 |  |  |  | Bed Truck
162 | Rig Up | Spot Pipe Bin 4 | 161 | 29 | 18 |  |  |  | Bed Truck
163 | Rig Up | Spot Pipe Bin 5 | 162 | 30 | 18 |  |  |  | Bed Truck
164 | Rig Up | Spot Pipe Bin 6 | 163 | 31 | 18 |  |  |  | Bed Truck
165 | Rig Up | Spot HWDP / Collars | 164 | 32 | 20 |  |  |  | Bed Truck
166 | Rig Up | Spot Casing Bins | 165 | 34 | 22 |  |  |  | Bed Truck
167 | Rig Up | Strap & Tally Pipe | 166 | 0 | 0 |  |  |  | N/A
168 | Rig Up | Install Koomey Unit | 117 | 4 | 15 |  |  |  | Bed Truck
169 | Rig Up | Install Choke Manifold | 117 | 3 | 12 |  |  |  | Flatbed
170 | Rig Up | Run Control Lines (Hoses) | 168 | 0 | 5 |  |  |  | Flatbed
171 | Rig Up | Pressure Test Mud Lines | 150 | 0 | 0 |  |  |  | N/A
172 | Rig Up | Fill Water Tanks | 153 | 0 | 0 |  |  |  | Water Tanker
173 | Rig Up | Fill Fuel Tanks | 139 | 0 | 0 |  |  |  | Fuel Tanker
174 | Rig Up | Mix Spud Mud | 171 | 0 | 0 |  |  |  | N/A
175 | Rig Up | Spot BOP Stack (Cellar Area) | 133 | 2 | 35 |  |  |  | Lowboy
176 | Rig Up | Nipple Up BOP | 175 | 0 | 0 |  |  |  | N/A
177 | Rig Up | Test BOP (Pressure Test) | 176 | 0 | 0 |  |  |  | N/A
178 | Rig Up | Install Bell Nipple / Flowline | 176 | 6 | 4 |  |  |  | Flatbed
179 | Rig Up | Spot Third Party Cement | 104 | 86 | 25 |  |  |  | Bed Truck
180 | Rig Up | Spot Third Party Wireline | 104 | 87 | 20 |  |  |  | Bed Truck
181 | Rig Up | Spot Lighting Towers | 104 | 94 | 5 |  |  |  | Flatbed
182 | Rig Up | Rig Up Fire Safety System | 181 | 95 | 5 |  |  |  | Flatbed
183 | Rig Up | Install Wind Socks / Signs | 182 | 0 | 0 |  |  |  | N/A
184 | Rig Up | Safety Inspection (Walkaround) | 133 | 0 | 0 |  |  |  | N/A
185 | Rig Up | Electrical Inspection | 141 | 0 | 0 |  |  |  | N/A
186 | Rig Up | Mechanical Inspection | 171 | 0 | 0 |  |  |  | N/A
187 | Rig Up | Pre-Spud Meeting (Safety) | 184 | 0 | 0 |  |  |  | N/A
188 | Rig Up | Pick Up BHA (Bit/Motor) | 187 | 0 | 0 |  |  |  | N/A
189 | Rig Up | Make Up Drill String | 188 | 0 | 0 |  |  |  | N/A
190 | Rig Up | Install Drive Bushing | 189 | 0 | 0 |  |  |  | N/A
191 | Rig Up | Function Test Top Drive | 190 | 0 | 0 |  |  |  | N/A
192 | Rig Up | Review Emergency Response | 187 | 0 | 0 |  |  |  | N/A
193 | Rig Up | Final Aramco/Client Acceptance | 186 | 0 | 0 |  |  |  | N/A
194 | Rig Up | Open Permits | 193 | 0 | 0 |  |  |  | N/A
195 | Rig Up | Start Pumps (Circulate) | 194 | 0 | 0 |  |  |  | N/A
196 | Rig Up | Tag Bottom / Spud In | 195 | 0 | 0 |  |  |  | N/A
197 | Rig Up | Drill Surface Hole (Ops) | 196 | 0 | 0 |  |  |  | N/A
198 | Rig Up | Clear Camp Site A (Final) | 0 | 100 | 0 |  |  |  | Dump Truck
199 | Rig Up | Close Work Orders (Move) | 196 | 0 | 0 |  |  |  | N/A
200 | Rig Up | Submit Final Move Report | 199 | 0 | 0 |  |  |  | N/A