## Rig Loads
ID | Load Type | Description | Category | No. of Loads | Weight (tons) | Dimensions (L x W x H) | Priority | Rig Down Dependencies | Rig Up Dependencies | Avg Rig Down Time | Avg Rig Up Time | Critical Lift | Truck Type(s) | Minimum Crew (Rig Down / Rig Up) | Optimal Crew (Rig Down / Rig Up) | Optimal Avg Rig Down Time | Optimal Avg Rig Up Time
RL-01 | Rig | Sub-base & Substructure | Derrick & Drill Floor | 6 | 30 each | 14.55 x 7.73 x 6.00 m | 4 | RL-02, RL-03, RL-04, RL-05, RL-06 | — | 6.0 ± 2.0 hr/load | 8.0 ± 3.0 hr/load | Yes | Heavy Hauler / Low-bed | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | 4.50 ± 1.50 hr/load | 6.25 ± 2.25 hr/load
RL-02 | Rig | Mast | Derrick & Drill Floor | 8 | 15 each | 38.00 x 3.45 x 2.16 m | 3 | RL-03, RL-17, RL-18, RL-19, RL-20, RL-21, RL-23, RL-36 | RL-01, RL-03, RL-05, RL-06, RL-19, RL-21, RL-39 | 8.0 ± 2.0 hr/load | 10.0 ± 3.0 hr/load | Yes | Heavy Hauler | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | 6.00 ± 1.50 hr/load | 7.75 ± 2.25 hr/load
RL-03 | Rig | Set-back | Derrick & Drill Floor | 2 | 15 each | 6.00 x 3.00 x 2.00 m | 3 | RL-17, RL-18, RL-19, RL-20, RL-21 | RL-01 | 3.0 ± 1.0 hr/load | 4.0 ± 1.0 hr/load | Yes | Low-bed / Heavy Hauler | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | 2.25 ± 0.75 hr/load | 3.00 ± 0.75 hr/load
RL-04 | Rig | Draworks spreaders | Derrick & Drill Floor | 2 | 10 each | 9.00 x 1.50 x 1.50 m | 4 | RL-02 | RL-01 | 2.0 ± 1.0 hr/load | 2.0 ± 1.0 hr/load | No | Flat-bed | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | 1.50 ± 0.75 hr/load | 1.75 ± 0.75 hr/load
RL-05 | Rig | Draworks | Derrick & Drill Floor | 3 | 33, 27, & 11 Tons | 3.01 x 3.40 x 1.61 m | 4 | RL-02, RL-03, RL-04 | RL-01, RL-04 | 3.0 ± 1.0 hr/load | 4.0 ± 1.5 hr/load | Yes | Low-bed / Heavy Hauler | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | 2.25 ± 0.75 hr/load | 3.00 ± 1.00 hr/load
RL-06 | Rig | Rotary table & beam | Derrick & Drill Floor | 2 | 15 each | 3.00 x 2.50 x 1.20 m | 4 | RL-02, RL-03 | RL-01, RL-03 | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | No | Low-bed / Flat-bed | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | 1.50 ± 0.75 hr/load | 2.50 ± 0.75 hr/load
RL-07 | Rig | SCR House | Power & Utility Area | 1 | 25 | 8.60 x 2.80 x 2.35 m | 4 | — | RL-08, RL-10 | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | No | Low-bed / Flat-bed | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | 1.75 ± 0.75 hr/load | 2.50 ± 0.75 hr/load
RL-08 | Rig | Generator House | Power & Utility Area | 4 | 25 each | 12.00 x 3.00 x 3.20 m | 4 | — | — | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | No | Low-bed | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | 1.75 ± 0.75 hr/load | 2.50 ± 0.75 hr/load
RL-09 | Rig | Day Tank | Power & Utility Area | 1 | 20 | 6.00 x 2.50 x 2.50 m | 4 | — | RL-08, RL-10 | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | No | Flat-bed / Low-bed | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | 1.25 ± 0.50 hr/load | 1.75 ± 0.50 hr/load
RL-10 | Rig | Fuel Tank | Power & Utility Area | 2 | 20 each | 12.00 x 2.50 x 2.80 m | 4 | — | — | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | No | Flat-bed / Low-bed | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | 1.25 ± 0.50 hr/load | 1.75 ± 0.50 hr/load
RL-11 | Rig | Mud Pumps | Mud System & Tank Farm | 2 | 42 each | 4.12 x 2.44 x 1.81 m | 1 | — | RL-07, RL-08, RL-14 | 2.0 ± 1.0 hr/load | 3.5 ± 1.0 hr/load | Yes | Heavy Hauler / Low-bed | RD: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Rigger 1; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Riggers 2; Crane Operator 1; Electrician 1 | RD: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1; Welder 1 | 1.50 ± 0.75 hr/load | 2.75 ± 0.75 hr/load
RL-12 | Rig | Water Tanks | Mud System & Tank Farm | 3 | 15 each | 9.00 x 3.10 x 2.80 m | 1 | — | — | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | No | Flat-bed / Low-bed | RD: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 | 1.25 ± 0.50 hr/load | 1.75 ± 0.50 hr/load
RL-13 | Rig | Shaker Tank | Mud System & Tank Farm | 1 | 40 | 12.50 x 3.00 x 2.20 m | 1 | — | RL-14 | 3.0 ± 1.0 hr/load | 4.0 ± 1.0 hr/load | Yes | Heavy Hauler / Low-bed | RD: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Rigger 1; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Riggers 2; Crane Operator 1; Electrician 1 | RD: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1; Welder 1 | 2.50 ± 0.75 hr/load | 3.25 ± 0.75 hr/load
RL-14 | Rig | Mud Tanks | Mud System & Tank Farm | 4 | 23 each | 12.50 x 3.00 x 3.20 m | 1 | — | RL-12 | 2.5 ± 1.0 hr/load | 3.5 ± 1.0 hr/load | No | Low-bed / Heavy Hauler | RD: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Rigger 1; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Riggers 2; Crane Operator 1; Electrician 1 | RD: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1; Welder 1 | 2.00 ± 0.75 hr/load | 2.75 ± 0.75 hr/load
RL-15 | Rig | Tank ladders | Mud System & Tank Farm | 1 | 5 | 3.50 x 1.20 x 0.50 m | 5 | RL-14 | RL-14 | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | No | Flat-bed | RD: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 | 0.75 ± 0.50 hr/load | 0.75 ± 0.50 hr/load
RL-16 | Rig | Trip / Strip Tank | Mud System & Tank Farm | 1 | 15 | 6.00 x 2.50 x 2.50 m | 1 | — | RL-14 | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | No | Flat-bed / Low-bed | RD: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 | 1.25 ± 0.50 hr/load | 1.75 ± 0.50 hr/load
RL-17 | Rig | Catwalk | Derrick & Drill Floor | 2 | 10 each | 16.00 x 1.52 x 1.07 m | 2 | — | RL-02, RL-21 | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | No | Flat-bed | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | 1.50 ± 0.75 hr/load | 2.50 ± 0.75 hr/load
RL-18 | Rig | V-Door | Derrick & Drill Floor | 1 | 10 | 8.00 x 1.52 x 1.50 m | 2 | — | RL-02, RL-21 | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | No | Flat-bed | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | 0.75 ± 0.50 hr/load | 1.25 ± 0.50 hr/load
RL-19 | Rig | Floor ladders | Derrick & Drill Floor | 1 | 5 | 6.00 x 1.20 x 0.50 m | 2 | — | RL-21 | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | No | Flat-bed | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | 0.75 ± 0.50 hr/load | 0.75 ± 0.50 hr/load
RL-20 | Rig | Dog house | Camp, Cabins & Containers | 1 | 20 | 6.10 x 2.44 x 2.44 m | 2 | — | RL-21 | 1.5 ± 0.5 hr/load | 2.0 ± 1.0 hr/load | No | Flat-bed / Low-bed | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | 1.25 ± 0.50 hr/load | 1.75 ± 0.75 hr/load
RL-21 | Rig | Rig flooring & railings | Derrick & Drill Floor | 2 | 15 each | 6.70 x 6.00 x 1.20 m | 2 | RL-03 | RL-03, RL-05, RL-06 | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | No | Flat-bed | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | 1.50 ± 0.75 hr/load | 2.50 ± 0.75 hr/load
RL-22 | Rig | Beams | Derrick & Drill Floor | 1 | 15 | 12.00 x 1.20 x 1.20 m | 4 | RL-02 | RL-01, RL-03 | 2.0 ± 1.0 hr/load | 2.5 ± 1.0 hr/load | No | Flat-bed | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | 1.50 ± 0.75 hr/load | 2.00 ± 0.75 hr/load
RL-23 | Rig | Grass hopper | Derrick & Drill Floor | 1 | 15 | 8.00 x 2.50 x 2.00 m | 2 | — | RL-18 | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | No | Flat-bed | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | 0.75 ± 0.50 hr/load | 1.25 ± 0.50 hr/load
RL-24 | Rig | Cable trays | Power & Utility Area | 1 | 12 | 12.00 x 2.00 x 1.00 m | 4 | — | RL-07, RL-08 | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | No | Flat-bed | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | 0.75 ± 0.50 hr/load | 1.25 ± 0.50 hr/load
RL-25 | Rig | Koomey unit | Well Control Area | 1 | 20 | 4.39 x 2.00 x 2.64 m | 5 | — | RL-26, RL-07 | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | No | Low-bed / Flat-bed | RD: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; BOP Techs 2; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Techs 2; Floormen 4; Riggers 3; Crane Operator 1; Mechanic 1 | 1.50 ± 0.75 hr/load | 2.50 ± 0.75 hr/load
RL-26 | Rig | BOP Stack | Well Control Area | 1 | 30 | 2.85 x 1.27 x 3.00 m | 5 | — | RL-01 | 3.0 ± 1.0 hr/load | 4.0 ± 1.0 hr/load | Yes | Heavy Hauler / Low-bed | RD: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; BOP Techs 2; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Techs 2; Floormen 4; Riggers 3; Crane Operator 1; Mechanic 1 | 2.25 ± 0.75 hr/load | 3.25 ± 0.75 hr/load
RL-27 | Rig | Choke manifold | Well Control Area | 1 | 20 | 6.00 x 2.40 x 2.20 m | 5 | — | RL-25, RL-26 | 2.0 ± 1.0 hr/load | 2.5 ± 1.0 hr/load | No | Flat-bed / Low-bed | RD: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; BOP Techs 2; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Techs 2; Floormen 4; Riggers 3; Crane Operator 1; Mechanic 1 | 1.50 ± 0.75 hr/load | 2.00 ± 0.75 hr/load
RL-28 | Rig | Drill Line spool | Pipe Yard, Logistics & Support | 1 | 20 | 2.50 x 2.50 x 2.00 m | 5 | — | RL-02, RL-05 | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | No | Flat-bed | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | 0.75 ± 0.50 hr/load | 0.75 ± 0.50 hr/load
RL-29 | Rig | Fishing tool skid | Pipe Yard, Logistics & Support | 1 | 25 | 6.00 x 2.50 x 2.50 m | 1 | — | — | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | No | Flat-bed / Low-bed | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | 0.75 ± 0.50 hr/load | 0.75 ± 0.50 hr/load
RL-30 | Rig | Substitutes skid | Pipe Yard, Logistics & Support | 1 | 25 | 6.00 x 2.50 x 2.50 m | 3 | — | — | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | No | Flat-bed / Low-bed | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | 0.75 ± 0.50 hr/load | 0.75 ± 0.50 hr/load
RL-31 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 each | 12.00 x 2.50 x 2.50 m | 1 | — | — | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | No | Flat-bed | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load
RL-32 | Rig | Store containers | Camp, Cabins & Containers | 4 | 25 each | 12.19 x 2.44 x 2.90 m | 4 | — | — | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | No | Flat-bed / Low-bed | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | 1.25 ± 0.50 hr/load | 1.75 ± 0.50 hr/load
RL-33 | Rig | Rig office and Accommodation | Camp, Cabins & Containers | 3 | 30 each | 12.00 x 3.00 x 3.20 m | 4 | — | RL-07, RL-08 | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | No | Flat-bed / Low-bed | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | 1.75 ± 0.50 hr/load | 2.50 ± 0.75 hr/load
RL-34 | Rig | Primary and Secondary briefing Cabins | Camp, Cabins & Containers | 1 | 20 | 6.00 x 3.00 x 3.20 m | 4 | — | RL-33, RL-07 | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | No | Flat-bed / Low-bed | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | 1.25 ± 0.50 hr/load | 1.75 ± 0.50 hr/load
RL-35 | Rig | Welding shop | Camp, Cabins & Containers | 1 | 15 | 6.00 x 2.50 x 3.00 m | 5 | — | RL-07, RL-08 | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | No | Flat-bed / Low-bed | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | 1.25 ± 0.50 hr/load | 1.75 ± 0.50 hr/load
RL-36 | Rig | Pipe racks | Pipe Yard, Logistics & Support | 2 | 6 each | 9.10 x 1.20 x 1.20 m | 2 | — | RL-17 | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | No | Flat-bed | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | 0.75 ± 0.50 hr/load | 1.25 ± 0.50 hr/load
RL-37 | Rig | Crane | Pipe Yard, Logistics & Support | 1 | 30 | 12.00 x 3.00 x 3.80 m | 5 | — | — | 2.0 ± 1.0 hr/load | 2.0 ± 1.0 hr/load | No | Low-bed / Heavy Hauler | RD: Operator 1; Mechanic 1; Rigger 1 ¦ RU: Operator 1; Mechanic 1; Rigger 1 | RD: Operator 1; Mechanics 2; Rigger 1 ¦ RU: Operator 1; Mechanics 2; Rigger 1 | 1.75 ± 0.75 hr/load | 1.75 ± 0.75 hr/load
RL-38 | Rig | Fork lift | Pipe Yard, Logistics & Support | 1 | 15 | 5.50 x 2.30 x 2.80 m | 5 | — | — | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | No | Flat-bed / Low-bed | RD: Operator 1; Mechanic 1; Rigger 1 ¦ RU: Operator 1; Mechanic 1; Rigger 1 | RD: Operator 1; Mechanics 2; Rigger 1 ¦ RU: Operator 1; Mechanics 2; Rigger 1 | 0.75 ± 0.50 hr/load | 0.75 ± 0.50 hr/load
RL-39 | Rig | High & Low horse | Pipe Yard, Logistics & Support | 1 | 5 | 3.00 x 2.00 x 2.00 m | 5 | — | RL-01 | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | No | Flat-bed | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | 0.75 ± 0.50 hr/load | 0.75 ± 0.50 hr/load
RL-40 | Rig | Miscellaneous items | Pipe Yard, Logistics & Support | 10 | 10 each | 3.00 x 2.00 x 2.00 m | 6 | — | — | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load | No | Flat-bed | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | 0.50 ± 0.25 hr/load | 0.50 ± 0.25 hr/load
CL-01 | Camp | Caravans | Camp, Cabins & Containers | 9 | 25 each | 12.00 x 3.00 x 3.20 m | 7 | CL-02 | CL-02 | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | No | Flat-bed / Low-bed | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | 1.75 ± 0.50 hr/load | 2.50 ± 0.75 hr/load
CL-02 | Camp | Power house | Power & Utility Area | 1 | 20 | 12.00 x 3.00 x 3.20 m | 6 | CL-03 | CL-03 | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | No | Low-bed / Flat-bed | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | 1.75 ± 0.50 hr/load | 2.50 ± 0.75 hr/load
CL-03 | Camp | Fuel Tank | Power & Utility Area | 1 | 10 | 6.00 x 2.50 x 2.50 m | 6 | — | — | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | No | Flat-bed | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | 0.75 ± 0.50 hr/load | 1.25 ± 0.50 hr/load
CL-04 | Camp | Store container | Camp, Cabins & Containers | 1 | 25 | 12.19 x 2.44 x 2.90 m | 7 | — | — | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | No | Flat-bed / Low-bed | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | 1.25 ± 0.50 hr/load | 1.75 ± 0.50 hr/load
CL-05 | Camp | Spare motor skid | Power & Utility Area | 1 | 15 | 6.00 x 2.50 x 2.50 m | 7 | — | CL-02 | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | No | Low-bed / Flat-bed | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | 0.75 ± 0.50 hr/load | 1.25 ± 0.50 hr/load
CL-06 | Camp | Spare tool bin | Camp, Cabins & Containers | 1 | 15 | 6.00 x 2.50 x 2.50 m | 7 | — | — | 0.75 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | No | Flat-bed | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | 0.50 ± 0.25 hr/load | 0.75 ± 0.25 hr/load

## Additional Needed Loads
ID | Load Type | Description | No. of Loads | Weight (tons) | Dimensions (L x W x H) | Priority | Rig Up Dependencies | Avg Rig Up Time | Truck Type(s)
SU-01 | Startup | Drill pipe | 4 | 18 each | 13.50 x 2.50 x 2.50 m | 7 | RL-31, RL-36 | 6.0 ± 2.0 hr/load | Flat-bed / Low-bed
SU-02 | Startup | Drill collars / BHA tools | 2 | 20 each | 12.00 x 2.50 x 2.50 m | 7 | RL-31 | 5.0 ± 1.5 hr/load | Low-bed / Heavy Hauler
SU-03 | Startup | Drill bit | 1 | 2 | 2.00 x 1.50 x 1.50 m | 7 | SU-02 | 1.0 ± 0.5 hr/load | Flat-bed
SU-04 | Startup | Subs / crossovers / float subs | 1 | 3 | 2.50 x 1.80 x 1.80 m | 7 | SU-02 | 2.0 ± 0.5 hr/load | Flat-bed
SU-05 | Startup | Tubular handling tools | 2 | 8 each | 4.00 x 2.20 x 2.20 m | 6 | — | 3.0 ± 1.0 hr/load | Flat-bed
SU-06 | Startup | Tubular baskets / pipe accessories | 2 | 6 each | 6.00 x 2.40 x 2.40 m | 6 | RL-31 | 2.0 ± 0.5 hr/load | Flat-bed
SU-07 | Startup | Drilling fluid / spud mud | 4 | 25 each | 6.00 x 2.40 x 2.50 m | 7 | RL-14, RL-11 | 4.0 ± 1.0 hr/load | Flat-bed / Low-bed
SU-08 | Startup | Mud chemicals | 4 | 20 each | 6.00 x 2.40 x 2.50 m | 7 | RL-14 | 3.0 ± 1.0 hr/load | Flat-bed
SU-09 | Startup | Water / brine supply | 3 | 20 each | 6.00 x 2.40 x 2.50 m | 7 | RL-12 | 3.0 ± 1.0 hr/load | Low-bed
SU-10 | Startup | Diesel fuel | 2 | 20 each | 6.00 x 2.40 x 2.50 m | 7 | RL-10 | 2.0 ± 0.5 hr/load | Low-bed
SU-11 | Startup | Lubricants & hydraulic oil | 1 | 8 | 3.00 x 2.20 x 2.20 m | 6 | — | 2.0 ± 0.5 hr/load | Flat-bed
SU-12 | Startup | Grease, filters & maintenance consumables | 1 | 3 | 2.50 x 2.00 x 2.00 m | 6 | — | 1.5 ± 0.5 hr/load | Flat-bed
SU-13 | Startup | Standpipe manifold parts & seals | 1 | 3 | 3.00 x 2.00 x 2.00 m | 6 | SU-13 | 2.0 ± 0.5 hr/load | Flat-bed
SU-14 | Startup | BOP test equipment | 1 | 12 | 4.00 x 2.40 x 2.50 m | 7 | RL-26 | 3.0 ± 1.0 hr/load | Low-bed
SU-15 | Startup | Top drive package / Kelly package | 1 | 18 | 7.00 x 2.80 x 3.20 m | 6 | RL-01, RL-02, RL-06 | 6.0 ± 2.0 hr/load | Low-bed / Heavy Hauler

## Trucks Info
Truck Type | Maximum Weight (tons) | Approx. Truck Dimensions (L x W x H, m) | Average Speed (km/h) | α
Flat-bed | 25 (planning estimate) | 16.0 x 2.6 x 3.5 | 50 | 0.3-0.4
Low-bed | 40 (planning estimate) | 18.0 x 3.0 x 3.6 | 40 | 0.25-0.35
Heavy Hauler | 60 (planning estimate) | 20.0 x 3.2 x 3.8 | 30 | 0.35-0.5
Vnew​=Vavg(1−α×Wload​/Wmax)