## Expanded Loads
Load ID | Load Type | Description | Category | Total Loads in Task | Weight (tons) | Dimensions (L x W x H) | Priority | Truck Type(s) | Critical Lift | Avg Rig Down Time | Avg Rig Up Time | Sequential Predecessor | Rig Down Predecessor(s) | Rig Up Predecessor(s) | Minimum Crew (Rig Down / Rig Up) | Optimal Crew (Rig Down / Rig Up) | Truck Validation Note
RL-01-L1 | Rig | Sub-base & Substructure | Derrick & Drill Floor | 6 | 30 | 14.55 x 3.1 x 3.5 m | 4 | Heavy Hauler (Double Axle) | Yes | 6.0 ± 2.0 hr/load | 8.0 ± 3.0 hr/load | — | RL-02-L8, RL-03-L2, RL-04-L2, RL-05-L3, RL-06-L2 | — | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-01-L2 | Rig | Sub-base & Substructure | Derrick & Drill Floor | 6 | 30 | 14.55 x 3.1 x 3.5 m | 4 | Heavy Hauler (Double Axle) | Yes | 6.0 ± 2.0 hr/load | 8.0 ± 3.0 hr/load | RL-01-L1 | RL-01-L1 | RL-01-L1 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-01-L3 | Rig | Sub-base & Substructure | Derrick & Drill Floor | 6 | 30 | 14.55 x 3.1 x 3.5 m | 4 | Heavy Hauler (Double Axle) | Yes | 6.0 ± 2.0 hr/load | 8.0 ± 3.0 hr/load | RL-01-L2 | RL-01-L2 | RL-01-L2 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-01-L4 | Rig | Sub-base & Substructure | Derrick & Drill Floor | 6 | 30 | 14.55 x 3.1 x 3.5 m | 4 | Heavy Hauler (Double Axle) | Yes | 6.0 ± 2.0 hr/load | 8.0 ± 3.0 hr/load | RL-01-L3 | RL-01-L3 | RL-01-L3 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-01-L5 | Rig | Sub-base & Substructure | Derrick & Drill Floor | 6 | 30 | 14.55 x 3.1 x 3.5 m | 4 | Heavy Hauler (Double Axle) | Yes | 6.0 ± 2.0 hr/load | 8.0 ± 3.0 hr/load | RL-01-L4 | RL-01-L4 | RL-01-L4 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-01-L6 | Rig | Sub-base & Substructure | Derrick & Drill Floor | 6 | 30 | 14.55 x 3.1 x 3.5 m | 4 | Heavy Hauler (Double Axle) | Yes | 6.0 ± 2.0 hr/load | 8.0 ± 3.0 hr/load | RL-01-L5 | RL-01-L5 | RL-01-L5 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-02-L1 | Rig | Mast | Derrick & Drill Floor | 8 | 15 | 20.00 x 3.2 x 2.16 m | 3 | Heavy Hauler (Double Axle) | Yes | 8.0 ± 2.0 hr/load | 10.0 ± 3.0 hr/load | — | RL-03-L2, RL-17-L2, RL-18-L1, RL-19-L1, RL-20-L1, RL-21-L2, RL-23-L1, RL-36-L2 | RL-01-L6, RL-03-L2, RL-05-L3, RL-06-L2, RL-19-L1, RL-21-L2, RL-39-L1 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-02-L2 | Rig | Mast | Derrick & Drill Floor | 8 | 15 | 20.00 x 3.2 x 2.16 m | 3 | Heavy Hauler (Double Axle) | Yes | 8.0 ± 2.0 hr/load | 10.0 ± 3.0 hr/load | RL-02-L1 | RL-02-L1 | RL-02-L1 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-02-L3 | Rig | Mast | Derrick & Drill Floor | 8 | 15 | 20.00 x 3.2 x 2.16 m | 3 | Heavy Hauler (Double Axle) | Yes | 8.0 ± 2.0 hr/load | 10.0 ± 3.0 hr/load | RL-02-L2 | RL-02-L2 | RL-02-L2 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-02-L4 | Rig | Mast | Derrick & Drill Floor | 8 | 15 | 20.00 x 3.2 x 2.16 m | 3 | Heavy Hauler (Double Axle) | Yes | 8.0 ± 2.0 hr/load | 10.0 ± 3.0 hr/load | RL-02-L3 | RL-02-L3 | RL-02-L3 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-02-L5 | Rig | Mast | Derrick & Drill Floor | 8 | 15 | 20.00 x 3.2 x 2.16 m | 3 | Heavy Hauler (Double Axle) | Yes | 8.0 ± 2.0 hr/load | 10.0 ± 3.0 hr/load | RL-02-L4 | RL-02-L4 | RL-02-L4 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-02-L6 | Rig | Mast | Derrick & Drill Floor | 8 | 15 | 20.00 x 3.2 x 2.16 m | 3 | Heavy Hauler (Double Axle) | Yes | 8.0 ± 2.0 hr/load | 10.0 ± 3.0 hr/load | RL-02-L5 | RL-02-L5 | RL-02-L5 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-02-L7 | Rig | Mast | Derrick & Drill Floor | 8 | 15 | 20.00 x 3.2 x 2.16 m | 3 | Heavy Hauler (Double Axle) | Yes | 8.0 ± 2.0 hr/load | 10.0 ± 3.0 hr/load | RL-02-L6 | RL-02-L6 | RL-02-L6 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-02-L8 | Rig | Mast | Derrick & Drill Floor | 8 | 15 | 20.00 x 3.2 x 2.16 m | 3 | Heavy Hauler (Double Axle) | Yes | 8.0 ± 2.0 hr/load | 10.0 ± 3.0 hr/load | RL-02-L7 | RL-02-L7 | RL-02-L7 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-03-L1 | Rig | Set-back | Derrick & Drill Floor | 2 | 15 | 6.00 x 3.00 x 2.00 m | 3 | Low-bed (Double Axle) | Yes | 3.0 ± 1.0 hr/load | 4.0 ± 1.0 hr/load | — | RL-17-L2, RL-18-L1, RL-19-L1, RL-20-L1, RL-21-L2 | RL-01-L6 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-03-L2 | Rig | Set-back | Derrick & Drill Floor | 2 | 15 | 6.00 x 3.00 x 2.00 m | 3 | Low-bed (Double Axle) | Yes | 3.0 ± 1.0 hr/load | 4.0 ± 1.0 hr/load | RL-03-L1 | RL-03-L1 | RL-03-L1 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OK — validated
RL-04-L1 | Rig | Draworks spreaders | Derrick & Drill Floor | 2 | 10 | 9.00 x 1.50 x 1.50 m | 4 | Flat-bed (Single Axle) | No | 2.0 ± 1.0 hr/load | 2.0 ± 1.0 hr/load | — | RL-02-L8 | RL-01-L6 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | OK — validated
RL-04-L2 | Rig | Draworks spreaders | Derrick & Drill Floor | 2 | 10 | 9.00 x 1.50 x 1.50 m | 4 | Flat-bed (Single Axle) | No | 2.0 ± 1.0 hr/load | 2.0 ± 1.0 hr/load | RL-04-L1 | RL-04-L1 | RL-04-L1 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | OK — validated
RL-05-L1 | Rig | Draworks | Derrick & Drill Floor | 3 | 33 | 3.01 x 3.20 x 1.61 m | 4 | Heavy Hauler (Double Axle) | Yes | 3.0 ± 1.0 hr/load | 4.0 ± 1.5 hr/load | — | RL-02-L8, RL-03-L2, RL-04-L2 | RL-01-L6, RL-04-L2 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OVERSIZED: W=3.4m exceeds all truck types. Heavy Hauler assigned as closest fit. Special transport permit required.
RL-05-L2 | Rig | Draworks | Derrick & Drill Floor | 3 | 27 | 3.01 x 3.20 x 1.61 m | 4 | Heavy Hauler (Double Axle) | Yes | 3.0 ± 1.0 hr/load | 4.0 ± 1.5 hr/load | RL-05-L1 | RL-05-L1 | RL-05-L1 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OVERSIZED: W=3.4m exceeds all truck types. Heavy Hauler assigned as closest fit. Special transport permit required.
RL-05-L3 | Rig | Draworks | Derrick & Drill Floor | 3 | 11 | 3.01 x 3.20 x 1.61 m | 4 | Heavy Hauler (Double Axle) | Yes | 3.0 ± 1.0 hr/load | 4.0 ± 1.5 hr/load | RL-05-L2 | RL-05-L2 | RL-05-L2 | RD: Driller 1; Asst. Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 4; Riggers 3; Crane Operators 2; Mechanic 1 | RD: Driller 1; Asst. Driller 1; Floormen 6; Riggers 3; Crane Operators 2; Mechanic 2; Welder 1 ¦ RU: Driller 1; Asst. Driller 1; Floormen 6; Riggers 4; Crane Operators 3; Mechanic 2; Welder 1 | OVERSIZED: W=3.4m exceeds all truck types. Heavy Hauler assigned as closest fit. Special transport permit required.
RL-06-L1 | Rig | Rotary table & beam | Derrick & Drill Floor | 2 | 15 | 3.00 x 2.50 x 1.20 m | 4 | Flat-bed (Single Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | — | RL-02-L8, RL-03-L2 | RL-01-L6, RL-03-L2 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | CORRECTED: truck type updated per weight+dimension validation
RL-06-L2 | Rig | Rotary table & beam | Derrick & Drill Floor | 2 | 15 | 3.00 x 2.50 x 1.20 m | 4 | Flat-bed (Single Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | RL-06-L1 | RL-06-L1 | RL-06-L1 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | CORRECTED: truck type updated per weight+dimension validation
RL-07-L1 | Rig | SCR House | Power & Utility Area | 1 | 25 | 8.60 x 2.80 x 2.35 m | 4 | Low-bed (Double Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | — | — | RL-08-L4, RL-10-L2 | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | CORRECTED: truck type updated per weight+dimension validation
RL-08-L1 | Rig | Generator House | Power & Utility Area | 4 | 25 | 12.00 x 3.00 x 3.20 m | 4 | Low-bed (Double Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | — | — | — | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | OK — validated
RL-08-L2 | Rig | Generator House | Power & Utility Area | 4 | 25 | 12.00 x 3.00 x 3.20 m | 4 | Low-bed (Double Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | RL-08-L1 | RL-08-L1 | RL-08-L1 | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | OK — validated
RL-08-L3 | Rig | Generator House | Power & Utility Area | 4 | 25 | 12.00 x 3.00 x 3.20 m | 4 | Low-bed (Double Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | RL-08-L2 | RL-08-L2 | RL-08-L2 | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | OK — validated
RL-08-L4 | Rig | Generator House | Power & Utility Area | 4 | 25 | 12.00 x 3.00 x 3.20 m | 4 | Low-bed (Double Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | RL-08-L3 | RL-08-L3 | RL-08-L3 | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | OK — validated
RL-09-L1 | Rig | Day Tank | Power & Utility Area | 1 | 20 | 6.00 x 2.50 x 2.50 m | 4 | Flat-bed (Single Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | — | — | RL-08-L4, RL-10-L2 | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | OK — validated
RL-10-L1 | Rig | Fuel Tank | Power & Utility Area | 2 | 20 | 12.00 x 2.50 x 2.80 m | 4 | Flat-bed (Single Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | — | — | — | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | OK — validated
RL-10-L2 | Rig | Fuel Tank | Power & Utility Area | 2 | 20 | 12.00 x 2.50 x 2.80 m | 4 | Flat-bed (Single Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | RL-10-L1 | RL-10-L1 | RL-10-L1 | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | OK — validated
RL-11-L1 | Rig | Mud Pumps | Mud System & Tank Farm | 2 | 42 | 4.12 x 2.44 x 1.81 m | 1 | Heavy Hauler (Double Axle) | Yes | 2.0 ± 1.0 hr/load | 3.5 ± 1.0 hr/load | — | — | RL-07-L1, RL-08-L4, RL-14-L4 | RD: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Rigger 1; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Riggers 2; Crane Operator 1; Electrician 1 | RD: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1; Welder 1 | OK — validated
RL-11-L2 | Rig | Mud Pumps | Mud System & Tank Farm | 2 | 42 | 4.12 x 2.44 x 1.81 m | 1 | Heavy Hauler (Double Axle) | Yes | 2.0 ± 1.0 hr/load | 3.5 ± 1.0 hr/load | RL-11-L1 | RL-11-L1 | RL-11-L1 | RD: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Rigger 1; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Riggers 2; Crane Operator 1; Electrician 1 | RD: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1; Welder 1 | OK — validated
RL-12-L1 | Rig | Water Tanks | Mud System & Tank Farm | 3 | 15 | 9.00 x 3.10 x 2.80 m | 1 | Heavy Hauler (Double Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | — | — | — | RD: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 | CORRECTED: truck type updated per weight+dimension validation
RL-12-L2 | Rig | Water Tanks | Mud System & Tank Farm | 3 | 15 | 9.00 x 3.10 x 2.80 m | 1 | Heavy Hauler (Double Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | RL-12-L1 | RL-12-L1 | RL-12-L1 | RD: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 | CORRECTED: truck type updated per weight+dimension validation
RL-12-L3 | Rig | Water Tanks | Mud System & Tank Farm | 3 | 15 | 9.00 x 3.10 x 2.80 m | 1 | Heavy Hauler (Double Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | RL-12-L2 | RL-12-L2 | RL-12-L2 | RD: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 | CORRECTED: truck type updated per weight+dimension validation
RL-13-L1 | Rig | Shaker Tank | Mud System & Tank Farm | 1 | 40 | 12.50 x 3.00 x 2.20 m | 1 | Low-bed (Double Axle) | Yes | 3.0 ± 1.0 hr/load | 4.0 ± 1.0 hr/load | — | — | RL-14-L4 | RD: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Rigger 1; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Riggers 2; Crane Operator 1; Electrician 1 | RD: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1; Welder 1 | OK — validated
RL-14-L1 | Rig | Mud Tanks | Mud System & Tank Farm | 4 | 23 | 12.50 x 3.00 x 3.20 m | 1 | Low-bed (Double Axle) | No | 2.5 ± 1.0 hr/load | 3.5 ± 1.0 hr/load | — | — | RL-12-L3 | RD: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Rigger 1; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Riggers 2; Crane Operator 1; Electrician 1 | RD: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1; Welder 1 | CORRECTED: truck type updated per weight+dimension validation
RL-14-L2 | Rig | Mud Tanks | Mud System & Tank Farm | 4 | 23 | 12.50 x 3.00 x 3.20 m | 1 | Low-bed (Double Axle) | No | 2.5 ± 1.0 hr/load | 3.5 ± 1.0 hr/load | RL-14-L1 | RL-14-L1 | RL-14-L1 | RD: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Rigger 1; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Riggers 2; Crane Operator 1; Electrician 1 | RD: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1; Welder 1 | CORRECTED: truck type updated per weight+dimension validation
RL-14-L3 | Rig | Mud Tanks | Mud System & Tank Farm | 4 | 23 | 12.50 x 3.00 x 3.20 m | 1 | Low-bed (Double Axle) | No | 2.5 ± 1.0 hr/load | 3.5 ± 1.0 hr/load | RL-14-L2 | RL-14-L2 | RL-14-L2 | RD: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Rigger 1; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Riggers 2; Crane Operator 1; Electrician 1 | RD: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1; Welder 1 | CORRECTED: truck type updated per weight+dimension validation
RL-14-L4 | Rig | Mud Tanks | Mud System & Tank Farm | 4 | 23 | 12.50 x 3.00 x 3.20 m | 1 | Low-bed (Double Axle) | No | 2.5 ± 1.0 hr/load | 3.5 ± 1.0 hr/load | RL-14-L3 | RL-14-L3 | RL-14-L3 | RD: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Rigger 1; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 1; Floormen 3; Riggers 2; Crane Operator 1; Electrician 1 | RD: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1 ¦ RU: Derrickman 1; Pumpman/Mechanic 2; Floormen 4; Riggers 2; Crane Operator 1; Electrician 1; Welder 1 | CORRECTED: truck type updated per weight+dimension validation
RL-15-L1 | Rig | Tank ladders | Mud System & Tank Farm | 1 | 5 | 3.50 x 1.20 x 0.50 m | 5 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | — | RL-14-L4 | RL-14-L4 | RD: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 | OK — validated
RL-16-L1 | Rig | Trip / Strip Tank | Mud System & Tank Farm | 1 | 15 | 6.00 x 2.50 x 2.50 m | 1 | Flat-bed (Single Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | — | — | RL-14-L4 | RD: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Derrickman 1; Floormen 3; Riggers 2; Crane Operator 1 | CORRECTED: truck type updated per weight+dimension validation
RL-17-L1 | Rig | Catwalk | Derrick & Drill Floor | 2 | 10 | 16.00 x 1.52 x 1.07 m | 2 | Flat-bed (Single Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | — | — | RL-02-L8, RL-21-L2 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | OK — validated
RL-17-L2 | Rig | Catwalk | Derrick & Drill Floor | 2 | 10 | 16.00 x 1.52 x 1.07 m | 2 | Flat-bed (Single Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | RL-17-L1 | RL-17-L1 | RL-17-L1 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | OK — validated
RL-18-L1 | Rig | V-Door | Derrick & Drill Floor | 1 | 10 | 8.00 x 1.52 x 1.50 m | 2 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | — | — | RL-02-L8, RL-21-L2 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | OK — validated
RL-19-L1 | Rig | Floor ladders | Derrick & Drill Floor | 1 | 5 | 6.00 x 1.20 x 0.50 m | 2 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | — | — | RL-21-L2 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | OK — validated
RL-20-L1 | Rig | Dog house | Camp, Cabins & Containers | 1 | 20 | 6.10 x 2.44 x 2.44 m | 2 | Flat-bed (Single Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 1.0 hr/load | — | — | RL-21-L2 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | CORRECTED: truck type updated per weight+dimension validation
RL-21-L1 | Rig | Rig flooring & railings | Derrick & Drill Floor | 2 | 15 | 6.70 x 5.9. x 1.20 m | 2 | Heavy Hauler (Double Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | — | — | RL-03-L2, RL-05-L3, RL-06-L2 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | OVERSIZED: W=6.0m exceeds all truck types. Heavy Hauler assigned as closest fit. Special wide-load permit required.
RL-21-L2 | Rig | Rig flooring & railings | Derrick & Drill Floor | 2 | 15 | 6.70 x 5.9. x 1.20 m | 2 | Heavy Hauler (Double Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | RL-21-L1 | RL-21-L1 | RL-21-L1 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | OVERSIZED: W=6.0m exceeds all truck types. Heavy Hauler assigned as closest fit. Special wide-load permit required.
RL-22-L1 | Rig | Beams | Derrick & Drill Floor | 1 | 15 | 12.00 x 1.20 x 1.20 m | 4 | Flat-bed (Single Axle) | No | 2.0 ± 1.0 hr/load | 2.5 ± 1.0 hr/load | — | RL-02-L8 | RL-01-L6, RL-03-L2 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | OK — validated
RL-23-L1 | Rig | Grass hopper | Derrick & Drill Floor | 1 | 15 | 8.00 x 2.50 x 2.00 m | 2 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | — | — | RL-18-L1 | RD: Driller 1; Floormen 3; Rigger 1; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; Floormen 4; Riggers 2; Crane Operators 2; Mechanic 1 | OK — validated
RL-24-L1 | Rig | Cable trays | Power & Utility Area | 1 | 12 | 12.00 x 2.00 x 1.00 m | 4 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | — | — | RL-07-L1, RL-08-L4 | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | OK — validated
RL-25-L1 | Rig | Koomey unit | Well Control Area | 1 | 20 | 4.39 x 2.00 x 2.64 m | 5 | Flat-bed (Single Axle) | No | 2.0 ± 1.0 hr/load | 3.0 ± 1.0 hr/load | — | — | RL-26-L1, RL-07-L1 | RD: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; BOP Techs 2; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Techs 2; Floormen 4; Riggers 3; Crane Operator 1; Mechanic 1 | CORRECTED: truck type updated per weight+dimension validation
RL-26-L1 | Rig | BOP Stack | Well Control Area | 1 | 30 | 2.85 x 1.27 x 3.00 m | 5 | Low-bed (Double Axle) | Yes | 3.0 ± 1.0 hr/load | 4.0 ± 1.0 hr/load | — | — | RL-01-L6 | RD: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; BOP Techs 2; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Techs 2; Floormen 4; Riggers 3; Crane Operator 1; Mechanic 1 | OK — validated
RL-27-L1 | Rig | Choke manifold | Well Control Area | 1 | 20 | 6.00 x 2.40 x 2.20 m | 5 | Flat-bed (Single Axle) | No | 2.0 ± 1.0 hr/load | 2.5 ± 1.0 hr/load | — | — | RL-25-L1, RL-26-L1 | RD: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Tech 1; Floormen 3; Riggers 2; Crane Operator 1; Mechanic 1 | RD: Driller 1; BOP Techs 2; Floormen 4; Riggers 2; Crane Operator 1; Mechanic 1 ¦ RU: Driller 1; BOP Techs 2; Floormen 4; Riggers 3; Crane Operator 1; Mechanic 1 | CORRECTED: truck type updated per weight+dimension validation
RL-28-L1 | Rig | Drill Line spool | Pipe Yard, Logistics & Support | 1 | 20 | 2.50 x 2.50 x 2.00 m | 5 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | — | — | RL-02-L8, RL-05-L3 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-29-L1 | Rig | Fishing tool skid | Pipe Yard, Logistics & Support | 1 | 25 | 6.00 x 2.50 x 2.50 m | 1 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | — | — | — | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-30-L1 | Rig | Substitutes skid | Pipe Yard, Logistics & Support | 1 | 25 | 6.00 x 2.50 x 2.50 m | 3 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | — | — | — | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-31-L1 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | — | — | — | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L2 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L1 | RL-31-L1 | RL-31-L1 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L3 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L2 | RL-31-L2 | RL-31-L2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L4 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L3 | RL-31-L3 | RL-31-L3 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L5 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L4 | RL-31-L4 | RL-31-L4 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L6 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L5 | RL-31-L5 | RL-31-L5 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L7 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L6 | RL-31-L6 | RL-31-L6 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L8 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L7 | RL-31-L7 | RL-31-L7 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L9 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L8 | RL-31-L8 | RL-31-L8 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L10 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L9 | RL-31-L9 | RL-31-L9 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L11 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L10 | RL-31-L10 | RL-31-L10 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L12 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L11 | RL-31-L11 | RL-31-L11 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L13 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L12 | RL-31-L12 | RL-31-L12 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-31-L14 | Rig | Pipe bins | Pipe Yard, Logistics & Support | 14 | 30 | 12.00 x 2.50 x 2.50 m | 1 | Low-bed (Double Axle) | No | 1.0 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | RL-31-L13 | RL-31-L13 | RL-31-L13 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | CORRECTED: truck type updated per weight+dimension validation
RL-32-L1 | Rig | Store containers | Camp, Cabins & Containers | 4 | 25 | 12.19 x 2.44 x 2.90 m | 4 | Flat-bed (Single Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | — | — | — | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | CORRECTED: truck type updated per weight+dimension validation
RL-32-L2 | Rig | Store containers | Camp, Cabins & Containers | 4 | 25 | 12.19 x 2.44 x 2.90 m | 4 | Flat-bed (Single Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | RL-32-L1 | RL-32-L1 | RL-32-L1 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | CORRECTED: truck type updated per weight+dimension validation
RL-32-L3 | Rig | Store containers | Camp, Cabins & Containers | 4 | 25 | 12.19 x 2.44 x 2.90 m | 4 | Flat-bed (Single Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | RL-32-L2 | RL-32-L2 | RL-32-L2 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | CORRECTED: truck type updated per weight+dimension validation
RL-32-L4 | Rig | Store containers | Camp, Cabins & Containers | 4 | 25 | 12.19 x 2.44 x 2.90 m | 4 | Flat-bed (Single Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | RL-32-L3 | RL-32-L3 | RL-32-L3 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | CORRECTED: truck type updated per weight+dimension validation
RL-33-L1 | Rig | Rig office and Accommodation | Camp, Cabins & Containers | 3 | 30 | 12.00 x 3.00 x 3.20 m | 4 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | — | — | RL-07-L1, RL-08-L4 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
RL-33-L2 | Rig | Rig office and Accommodation | Camp, Cabins & Containers | 3 | 30 | 12.00 x 3.00 x 3.20 m | 4 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | RL-33-L1 | RL-33-L1 | RL-33-L1 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
RL-33-L3 | Rig | Rig office and Accommodation | Camp, Cabins & Containers | 3 | 30 | 12.00 x 3.00 x 3.20 m | 4 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | RL-33-L2 | RL-33-L2 | RL-33-L2 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
RL-34-L1 | Rig | Primary and Secondary briefing Cabins | Camp, Cabins & Containers | 1 | 20 | 6.00 x 3.00 x 3.20 m | 4 | Low-bed (Double Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | — | — | RL-33-L3, RL-07-L1 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
RL-35-L1 | Rig | Welding shop | Camp, Cabins & Containers | 1 | 15 | 6.00 x 2.50 x 3.00 m | 5 | Flat-bed (Single Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | — | — | RL-07-L1, RL-08-L4 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | CORRECTED: truck type updated per weight+dimension validation
RL-36-L1 | Rig | Pipe racks | Pipe Yard, Logistics & Support | 2 | 6 | 9.10 x 1.20 x 1.20 m | 2 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | — | — | RL-17-L2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-36-L2 | Rig | Pipe racks | Pipe Yard, Logistics & Support | 2 | 6 | 9.10 x 1.20 x 1.20 m | 2 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | RL-36-L1 | RL-36-L1 | RL-36-L1 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-37-L1 | Rig | Crane | Pipe Yard, Logistics & Support | 1 | 30 | 12.00 x 3.00 x 3.80 m | 5 | Heavy Hauler (Double Axle) | No | 2.0 ± 1.0 hr/load | 2.0 ± 1.0 hr/load | — | — | — | RD: Operator 1; Mechanic 1; Rigger 1 ¦ RU: Operator 1; Mechanic 1; Rigger 1 | RD: Operator 1; Mechanics 2; Rigger 1 ¦ RU: Operator 1; Mechanics 2; Rigger 1 | OK — validated
RL-38-L1 | Rig | Fork lift | Pipe Yard, Logistics & Support | 1 | 15 | 5.50 x 2.30 x 2.80 m | 5 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | — | — | — | RD: Operator 1; Mechanic 1; Rigger 1 ¦ RU: Operator 1; Mechanic 1; Rigger 1 | RD: Operator 1; Mechanics 2; Rigger 1 ¦ RU: Operator 1; Mechanics 2; Rigger 1 | OK — validated
RL-39-L1 | Rig | High & Low horse | Pipe Yard, Logistics & Support | 1 | 5 | 3.00 x 2.00 x 2.00 m | 5 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.0 ± 0.5 hr/load | — | — | RL-01-L6 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-40-L1 | Rig | Miscellaneous items | Pipe Yard, Logistics & Support | 10 | 10 | 3.00 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | No | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load | — | — | — | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-40-L2 | Rig | Miscellaneous items | Pipe Yard, Logistics & Support | 10 | 10 | 3.00 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | No | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load | RL-40-L1 | RL-40-L1 | RL-40-L1 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-40-L3 | Rig | Miscellaneous items | Pipe Yard, Logistics & Support | 10 | 10 | 3.00 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | No | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load | RL-40-L2 | RL-40-L2 | RL-40-L2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-40-L4 | Rig | Miscellaneous items | Pipe Yard, Logistics & Support | 10 | 10 | 3.00 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | No | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load | RL-40-L3 | RL-40-L3 | RL-40-L3 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-40-L5 | Rig | Miscellaneous items | Pipe Yard, Logistics & Support | 10 | 10 | 3.00 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | No | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load | RL-40-L4 | RL-40-L4 | RL-40-L4 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-40-L6 | Rig | Miscellaneous items | Pipe Yard, Logistics & Support | 10 | 10 | 3.00 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | No | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load | RL-40-L5 | RL-40-L5 | RL-40-L5 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-40-L7 | Rig | Miscellaneous items | Pipe Yard, Logistics & Support | 10 | 10 | 3.00 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | No | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load | RL-40-L6 | RL-40-L6 | RL-40-L6 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-40-L8 | Rig | Miscellaneous items | Pipe Yard, Logistics & Support | 10 | 10 | 3.00 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | No | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load | RL-40-L7 | RL-40-L7 | RL-40-L7 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-40-L9 | Rig | Miscellaneous items | Pipe Yard, Logistics & Support | 10 | 10 | 3.00 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | No | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load | RL-40-L8 | RL-40-L8 | RL-40-L8 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
RL-40-L10 | Rig | Miscellaneous items | Pipe Yard, Logistics & Support | 10 | 10 | 3.00 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | No | 0.75 ± 0.25 hr/load | 0.75 ± 0.25 hr/load | RL-40-L9 | RL-40-L9 | RL-40-L9 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 2 | RD: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 ¦ RU: Yard Foreman 1; Forklift/Crane Operator 1; Roustabouts 3 | OK — validated
CL-01-L1 | Camp | Caravans | Camp, Cabins & Containers | 9 | 25 | 12.00 x 3.00 x 3.20 m | 7 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | — | CL-02-L1 | CL-02-L1 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
CL-01-L2 | Camp | Caravans | Camp, Cabins & Containers | 9 | 25 | 12.00 x 3.00 x 3.20 m | 7 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | CL-01-L1 | CL-01-L1 | CL-01-L1 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
CL-01-L3 | Camp | Caravans | Camp, Cabins & Containers | 9 | 25 | 12.00 x 3.00 x 3.20 m | 7 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | CL-01-L2 | CL-01-L2 | CL-01-L2 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
CL-01-L4 | Camp | Caravans | Camp, Cabins & Containers | 9 | 25 | 12.00 x 3.00 x 3.20 m | 7 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | CL-01-L3 | CL-01-L3 | CL-01-L3 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
CL-01-L5 | Camp | Caravans | Camp, Cabins & Containers | 9 | 25 | 12.00 x 3.00 x 3.20 m | 7 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | CL-01-L4 | CL-01-L4 | CL-01-L4 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
CL-01-L6 | Camp | Caravans | Camp, Cabins & Containers | 9 | 25 | 12.00 x 3.00 x 3.20 m | 7 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | CL-01-L5 | CL-01-L5 | CL-01-L5 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
CL-01-L7 | Camp | Caravans | Camp, Cabins & Containers | 9 | 25 | 12.00 x 3.00 x 3.20 m | 7 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | CL-01-L6 | CL-01-L6 | CL-01-L6 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
CL-01-L8 | Camp | Caravans | Camp, Cabins & Containers | 9 | 25 | 12.00 x 3.00 x 3.20 m | 7 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | CL-01-L7 | CL-01-L7 | CL-01-L7 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
CL-01-L9 | Camp | Caravans | Camp, Cabins & Containers | 9 | 25 | 12.00 x 3.00 x 3.20 m | 7 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | CL-01-L8 | CL-01-L8 | CL-01-L8 | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
CL-02-L1 | Camp | Power house | Power & Utility Area | 1 | 20 | 12.00 x 3.00 x 3.20 m | 6 | Low-bed (Double Axle) | No | 2.0 ± 0.5 hr/load | 3.0 ± 1.0 hr/load | — | CL-03-L1 | CL-03-L1 | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | OK — validated
CL-03-L1 | Camp | Fuel Tank | Power & Utility Area | 1 | 10 | 6.00 x 2.50 x 2.50 m | 6 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | — | — | — | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | OK — validated
CL-04-L1 | Camp | Store container | Camp, Cabins & Containers | 1 | 25 | 12.19 x 2.44 x 2.90 m | 7 | Flat-bed (Single Axle) | No | 1.5 ± 0.5 hr/load | 2.0 ± 0.5 hr/load | — | — | — | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated
CL-05-L1 | Camp | Spare motor skid | Power & Utility Area | 1 | 15 | 6.00 x 2.50 x 2.50 m | 7 | Flat-bed (Single Axle) | No | 1.0 ± 0.5 hr/load | 1.5 ± 0.5 hr/load | — | — | CL-02-L1 | RD: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 ¦ RU: Electrician 1; Mechanic 1; Floormen 2; Rigger 1; Crane Operator 1 | RD: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 ¦ RU: Electricians 2; Mechanics 2; Floormen 3; Riggers 2; Crane Operator 1 | CORRECTED: truck type updated per weight+dimension validation
CL-06-L1 | Camp | Spare tool bin | Camp, Cabins & Containers | 1 | 15 | 6.00 x 2.50 x 2.50 m | 7 | Flat-bed (Single Axle) | No | 0.75 ± 0.25 hr/load | 1.0 ± 0.25 hr/load | — | — | — | RD: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 2; Truck Driver 1; Crane Operator 1; Electrician 1 | RD: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1 ¦ RU: Camp Foreman 1; Roustabouts 3; Truck Driver 1; Crane Operator 1; Electrician 1 | OK — validated

## Expanded Additional Loads
Load ID | Load # | Load Type | Description | Weight (tons) | Dimensions (L x W x H) | Priority | Truck Type(s) | Avg Rig Up Time | Rig Up Predecessor(s)
SU-01-L1 | 1 | Startup | Drill pipe | 18 | 13.50 x 2.50 x 2.50 m | 7 | Flat-bed (Single Axle) | 6.0 ± 2.0 hr/load | RL-31-L14, RL-36-L2
SU-01-L2 | 2 | Startup | Drill pipe | 18 | 13.50 x 2.50 x 2.50 m | 7 | Flat-bed (Single Axle) | 6.0 ± 2.0 hr/load | SU-01-L1
SU-01-L3 | 3 | Startup | Drill pipe | 18 | 13.50 x 2.50 x 2.50 m | 7 | Flat-bed (Single Axle) | 6.0 ± 2.0 hr/load | SU-01-L2
SU-01-L4 | 4 | Startup | Drill pipe | 18 | 13.50 x 2.50 x 2.50 m | 7 | Flat-bed (Single Axle) | 6.0 ± 2.0 hr/load | SU-01-L3
SU-02-L1 | 1 | Startup | Drill collars / BHA tools | 20 | 12.00 x 2.50 x 2.50 m | 7 | Flat-bed (Single Axle) | 5.0 ± 1.5 hr/load | RL-31-L14
SU-02-L2 | 2 | Startup | Drill collars / BHA tools | 20 | 12.00 x 2.50 x 2.50 m | 7 | Flat-bed (Single Axle) | 5.0 ± 1.5 hr/load | SU-02-L1
SU-03-L1 | 1 | Startup | Drill bit | 2 | 2.00 x 1.50 x 1.50 m | 7 | Flat-bed (Single Axle) | 1.0 ± 0.5 hr/load | SU-02-L2
SU-04-L1 | 1 | Startup | Subs / crossovers / float subs | 3 | 2.50 x 1.80 x 1.80 m | 7 | Flat-bed (Single Axle) | 2.0 ± 0.5 hr/load | SU-02-L2
SU-05-L1 | 1 | Startup | Tubular handling tools | 8 | 4.00 x 2.20 x 2.20 m | 6 | Flat-bed (Single Axle) | 3.0 ± 1.0 hr/load | —
SU-05-L2 | 2 | Startup | Tubular handling tools | 8 | 4.00 x 2.20 x 2.20 m | 6 | Flat-bed (Single Axle) | 3.0 ± 1.0 hr/load | SU-05-L1
SU-06-L1 | 1 | Startup | Tubular baskets / pipe accessories | 6 | 6.00 x 2.40 x 2.40 m | 6 | Flat-bed (Single Axle) | 2.0 ± 0.5 hr/load | RL-31-L14
SU-06-L2 | 2 | Startup | Tubular baskets / pipe accessories | 6 | 6.00 x 2.40 x 2.40 m | 6 | Flat-bed (Single Axle) | 2.0 ± 0.5 hr/load | SU-06-L1
SU-07-L1 | 1 | Startup | Drilling fluid / spud mud | 25 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 4.0 ± 1.0 hr/load | RL-14-L4, RL-11-L2
SU-07-L2 | 2 | Startup | Drilling fluid / spud mud | 25 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 4.0 ± 1.0 hr/load | SU-07-L1
SU-07-L3 | 3 | Startup | Drilling fluid / spud mud | 25 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 4.0 ± 1.0 hr/load | SU-07-L2
SU-07-L4 | 4 | Startup | Drilling fluid / spud mud | 25 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 4.0 ± 1.0 hr/load | SU-07-L3
SU-08-L1 | 1 | Startup | Mud chemicals | 20 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 3.0 ± 1.0 hr/load | RL-14-L4
SU-08-L2 | 2 | Startup | Mud chemicals | 20 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 3.0 ± 1.0 hr/load | SU-08-L1
SU-08-L3 | 3 | Startup | Mud chemicals | 20 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 3.0 ± 1.0 hr/load | SU-08-L2
SU-08-L4 | 4 | Startup | Mud chemicals | 20 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 3.0 ± 1.0 hr/load | SU-08-L3
SU-09-L1 | 1 | Startup | Water / brine supply | 20 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 3.0 ± 1.0 hr/load | RL-12-L3
SU-09-L2 | 2 | Startup | Water / brine supply | 20 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 3.0 ± 1.0 hr/load | SU-09-L1
SU-09-L3 | 3 | Startup | Water / brine supply | 20 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 3.0 ± 1.0 hr/load | SU-09-L2
SU-10-L1 | 1 | Startup | Diesel fuel | 20 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 2.0 ± 0.5 hr/load | RL-10-L2
SU-10-L2 | 2 | Startup | Diesel fuel | 20 | 6.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 2.0 ± 0.5 hr/load | SU-10-L1
SU-11-L1 | 1 | Startup | Lubricants & hydraulic oil | 8 | 3.00 x 2.20 x 2.20 m | 6 | Flat-bed (Single Axle) | 2.0 ± 0.5 hr/load | —
SU-12-L1 | 1 | Startup | Grease, filters & maintenance consumables | 3 | 2.50 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | 1.5 ± 0.5 hr/load | —
SU-13-L1 | 1 | Startup | Standpipe manifold parts & seals | 3 | 3.00 x 2.00 x 2.00 m | 6 | Flat-bed (Single Axle) | 2.0 ± 0.5 hr/load | —
SU-14-L1 | 1 | Startup | BOP test equipment | 12 | 4.00 x 2.40 x 2.50 m | 7 | Flat-bed (Single Axle) | 3.0 ± 1.0 hr/load | RL-26-L1
SU-15-L1 | 1 | Startup | Top drive package / Kelly package | 18 | 7.00 x 2.80 x 3.20 m | 6 | Low-bed (Double Axle) | 6.0 ± 2.0 hr/load | RL-01-L6, RL-02-L8, RL-06-L2

## Trucks Info
Truck Type | Maximum Weight (tons) | Approx. Truck Dimensions (L x W x H, m) | Average Speed (km/h) | α
Flat-bed (Single Axle) | 25 (planning estimate) | 16.0 x 2.6 x 3.5 | 50 | 0.3-0.4
Low-bed (Double Axle) | 40 (planning estimate) | 18.0 x 3.0 x 3.6 | 40 | 0.25-0.35
Heavy Hauler (Double Axle) | 60 (planning estimate) | 20.0 x 3.2 x 3.8 | 30 | 0.35-0.5
Vnew​=Vavg(1−α×Wload​/Wmax)

## Shift Constraints
SHIFT & TIME CONSTRAINTS
SHIFT STRUCTURE
Parameter
Number of shifts per day | 2 | shifts/day | Fixed — cannot be changed
Shift duration | 12 | hours/shift | Each shift = 12 hours
Total working hours per day | 24 | hours/day | Shift 1 + Shift 2
SHIFT SCHEDULE
Shift
Shift 1 (Day) | 06:00 | 18:00 | 12 hours | YES | YES
Shift 2 (Night) | 18:00 | 06:00 | 12 hours | YES | NO — DARK (Safety)
TRANSPORT CONSTRAINT
Parameter
Transport allowed shifts | Shift 1 only | — | Rig moving NOT allowed at night (Shift 2)
Effective transport window/day | 12 | hours | Only during Shift 1 (06:00–18:00)
Max transport trips per day | #VALUE! | trips | Based on 0.59h one-way @ 20km
Round-trip time (20km) | 1.18 | hours | One-way 0.59h × 2
CPM IMPACT
Parameter
TR node duration | 0.59 | hours
If TR spans shift boundary | Defer to next Shift 1 | — | TR cannot start after 17:30 (needs 0.59h buffer before 18:00)
Daily schedule unit | 24 | hours | CPM durations remain in hours; shift logic applied in platform

## Truck Validation
TRUCK TYPE VALIDATION REPORT
Auto-generated validation against truck specs: Flat-bed ≤25t/16m, Low-bed ≤40t/18m, Heavy Hauler ≤60t/20m
Task ID | Description | Weight (t) | L x W x H (m) | Original Truck | Corrected Truck | Issue | Status
RL-01 | Sub-base & Substructure | 30 | 14.55x3.1x3.5 | Heavy Hauler | Heavy Hauler | — | ✓ OK
RL-02 | Mast | 15 | 20.00x3.2x2.16 | Heavy Hauler | Heavy Hauler | — | ✓ OK
RL-03 | Set-back | 15 | 6.00x3.00x2.00 | Low-bed | Low-bed | — | ✓ OK
RL-04 | Draworks spreaders | 10 | 9.00x1.50x1.50 | Flat-bed | Flat-bed | — | ✓ OK
RL-05 | Draworks | 33 | 3.01x3.40x1.61 | Heavy Hauler | Heavy Hauler | W=3.4m > all trucks | ⚠ OVERSIZED
RL-06 | Rotary table & beam | 15 | 3.00x2.50x1.20 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
RL-07 | SCR House | 25 | 8.60x2.80x2.35 | Flat-bed | Low-bed | W=2.8m > 2.6m | ✗ FIXED
RL-08 | Generator House | 25 | 12.00x3.00x3.20 | Low-bed | Low-bed | — | ✓ OK
RL-09 | Day Tank | 20 | 6.00x2.50x2.50 | Flat-bed | Flat-bed | — | ✓ OK
RL-10 | Fuel Tank | 20 | 12.00x2.50x2.80 | Flat-bed | Flat-bed | — | ✓ OK
RL-11 | Mud Pumps | 42 | 4.12x2.44x1.81 | Heavy Hauler | Heavy Hauler | — | ✓ OK
RL-12 | Water Tanks | 15 | 9.00x3.10x2.80 | Low-bed | Heavy Hauler | W=3.1m > 3.0m | ✗ FIXED
RL-13 | Shaker Tank | 40 | 12.50x3.00x2.20 | Low-bed | Low-bed | — | ✓ OK
RL-14 | Mud Tanks | 23 | 12.50x3.00x3.20 | Heavy Hauler | Low-bed | Over-assigned | ✗ FIXED
RL-15 | Tank ladders | 5 | 3.50x1.20x0.50 | Flat-bed | Flat-bed | — | ✓ OK
RL-16 | Trip/Strip Tank | 15 | 6.00x2.50x2.50 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
RL-17 | Catwalk | 10 | 16.00x1.52x1.07 | Flat-bed | Flat-bed | — | ✓ OK
RL-18 | V-Door | 10 | 8.00x1.52x1.50 | Flat-bed | Flat-bed | — | ✓ OK
RL-19 | Floor ladders | 5 | 6.00x1.20x0.50 | Flat-bed | Flat-bed | — | ✓ OK
RL-20 | Dog house | 20 | 6.10x2.44x2.44 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
RL-21 | Rig flooring & railings | 15 | 6.70x6.00x1.20 | Flat-bed | Heavy Hauler | W=6.0m > all trucks | ⚠ OVERSIZED
RL-22 | Beams | 15 | 12.00x1.20x1.20 | Flat-bed | Flat-bed | — | ✓ OK
RL-23 | Grass hopper | 15 | 8.00x2.50x2.00 | Flat-bed | Flat-bed | — | ✓ OK
RL-24 | Cable trays | 12 | 12.00x2.00x1.00 | Flat-bed | Flat-bed | — | ✓ OK
RL-25 | Koomey unit | 20 | 4.39x2.00x2.64 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
RL-26 | BOP Stack | 30 | 2.85x1.27x3.00 | Low-bed | Low-bed | — | ✓ OK
RL-27 | Choke manifold | 20 | 6.00x2.40x2.20 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
RL-28 | Drill Line spool | 20 | 2.50x2.50x2.00 | Flat-bed | Flat-bed | — | ✓ OK
RL-29 | Fishing tool skid | 25 | 6.00x2.50x2.50 | Flat-bed | Flat-bed | — | ✓ OK
RL-30 | Substitutes skid | 25 | 6.00x2.50x2.50 | Flat-bed | Flat-bed | — | ✓ OK
RL-31 | Pipe bins | 30 | 12.00x2.50x2.50 | Flat-bed | Low-bed | Wt 30t > 25t limit | ✗ FIXED
RL-32 | Store containers | 25 | 12.19x2.44x2.90 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
RL-33 | Rig office | 30 | 12.00x3.00x3.20 | Low-bed | Low-bed | — | ✓ OK
RL-34 | Briefing Cabins | 20 | 6.00x3.00x3.20 | Low-bed | Low-bed | — | ✓ OK
RL-35 | Welding shop | 15 | 6.00x2.50x3.00 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
RL-36 | Pipe racks | 6 | 9.10x1.20x1.20 | Flat-bed | Flat-bed | — | ✓ OK
RL-37 | Crane | 30 | 12.00x3.00x3.80 | Heavy Hauler | Heavy Hauler | — | ✓ OK
RL-38 | Fork lift | 15 | 5.50x2.30x2.80 | Flat-bed | Flat-bed | — | ✓ OK
RL-39 | High & Low horse | 5 | 3.00x2.00x2.00 | Flat-bed | Flat-bed | — | ✓ OK
RL-40 | Misc items | 10 | 3.00x2.00x2.00 | Flat-bed | Flat-bed | — | ✓ OK
CL-01 | Caravans | 25 | 12.00x3.00x3.20 | Low-bed | Low-bed | — | ✓ OK
CL-02 | Power house | 20 | 12.00x3.00x3.20 | Low-bed | Low-bed | — | ✓ OK
CL-03 | Fuel Tank (camp) | 10 | 6.00x2.50x2.50 | Flat-bed | Flat-bed | — | ✓ OK
CL-04 | Store container | 25 | 12.19x2.44x2.90 | Flat-bed | Flat-bed | — | ✓ OK
CL-05 | Spare motor skid | 15 | 6.00x2.50x2.50 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
CL-06 | Spare tool bin | 15 | 6.00x2.50x2.50 | Flat-bed | Flat-bed | — | ✓ OK
SU-01 | Drill pipe | 18 | 13.50x2.50x2.50 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
SU-02 | Drill collars | 20 | 12.00x2.50x2.50 | Heavy Hauler | Flat-bed | Over-assigned | ✗ FIXED
SU-03 | Drill bit | 2 | 2.00x1.50x1.50 | Flat-bed | Flat-bed | — | ✓ OK
SU-04 | Subs/crossovers | 3 | 2.50x1.80x1.80 | Flat-bed | Flat-bed | — | ✓ OK
SU-05 | Tubular handling tools | 8 | 4.00x2.20x2.20 | Flat-bed | Flat-bed | — | ✓ OK
SU-06 | Tubular baskets | 6 | 6.00x2.40x2.40 | Flat-bed | Flat-bed | — | ✓ OK
SU-07 | Drilling fluid | 25 | 6.00x2.40x2.50 | Flat-bed | Flat-bed | — | ✓ OK
SU-08 | Mud chemicals | 20 | 6.00x2.40x2.50 | Flat-bed | Flat-bed | — | ✓ OK
SU-09 | Water/brine supply | 20 | 6.00x2.40x2.50 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
SU-10 | Diesel fuel | 20 | 6.00x2.40x2.50 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
SU-11 | Lubricants | 8 | 3.00x2.20x2.20 | Flat-bed | Flat-bed | — | ✓ OK
SU-12 | Grease/filters | 3 | 2.50x2.00x2.00 | Flat-bed | Flat-bed | — | ✓ OK
SU-13 | Standpipe manifold | 3 | 3.00x2.00x2.00 | Flat-bed | Flat-bed | — | ✓ OK
SU-14 | BOP test equipment | 12 | 4.00x2.40x2.50 | Low-bed | Flat-bed | Over-assigned | ✗ FIXED
SU-15 | Top drive package | 18 | 7.00x2.80x3.20 | Low-bed | Low-bed | — | ✓ OK
SUMMARY: 61 tasks checked ¦ 42 OK ¦ 17 corrected ¦ 2 oversized flags